## Sheet1
sprint# | group# | group task description. | task# | task description | deviations (from original plan) | status | remarks
S01 | G01 | Backend scaffolding and FastAPI project setup | S01_G01_TB001 | Initialize backend repository with FastAPI project structure (src/app, tests, config folders). |  | pending
S01 | G01 | Backend scaffolding and FastAPI project setup | S01_G01_TB002 | Set up base FastAPI application with root and /health endpoints. |  | pending
S01 | G01 | Backend scaffolding and FastAPI project setup | S01_G01_TB003 | Configure environment-based settings (dev/prod) using pydantic settings or similar. |  | pending
S01 | G02 | Frontend scaffolding and React/TypeScript/Material UI setup | S01_G02_TF001 | Create React TypeScript app with Material UI and routing (React Router). |  | pending
S01 | G02 | Frontend scaffolding and React/TypeScript/Material UI setup | S01_G02_TF002 | Implement base layout with top bar and sidebar navigation placeholders. |  | pending
S01 | G02 | Frontend scaffolding and React/TypeScript/Material UI setup | S01_G02_TF003 | Wire basic API call from frontend to backend /health endpoint and display connection status. |  | pending
S01 | G03 | Tooling, Git workflow, and initial documentation | S01_G03_TB001 | Configure linting/formatting (black/isort/ruff) and pre-commit hooks for backend. |  | pending
S01 | G03 | Tooling, Git workflow, and initial documentation | S01_G03_TF002 | Configure linting/formatting (ESLint/Prettier) for frontend. |  | pending
S01 | G03 | Tooling, Git workflow, and initial documentation | S01_G03_TB003 | Create initial README with project overview and setup steps. |  | pending
S02 | G01 | Design core SQLite schema for alerts, orders, strategies, risk settings | S02_G01_TB001 | Design database schema for alerts, orders, strategies, risk_settings, positions, analytics_trades tables. |  | pending
S02 | G01 | Design core SQLite schema for alerts, orders, strategies, risk settings | S02_G01_TB002 | Review schema for extensibility and alignment with PRD (manual queue, risk, analytics). |  | pending
S02 | G02 | Implement ORM models and migrations | S02_G02_TB001 | Implement SQLAlchemy ORM models for core tables (alerts, orders, strategies, risk_settings). |  | pending
S02 | G02 | Implement ORM models and migrations | S02_G02_TB002 | Set up Alembic (or equivalent migration tool) for managing schema migrations. |  | pending
S02 | G02 | Implement ORM models and migrations | S02_G02_TB003 | Implement DB session management and dependency injection in FastAPI. |  | pending
S02 | G03 | Backend admin APIs for strategies and risk settings | S02_G03_TB001 | Create CRUD APIs to manage strategies (list/create/update). |  | pending
S02 | G03 | Backend admin APIs for strategies and risk settings | S02_G03_TB002 | Create CRUD APIs to manage global and per-strategy risk_settings. |  | pending
S02 | G03 | Backend admin APIs for strategies and risk settings | S02_G03_TF003 | Create simple admin UI to view strategies and risk_settings (read-only). |  | pending
S03 | G01 | TradingView webhook endpoint and alert validation | S03_G01_TB001 | Implement /webhook/tradingview endpoint that receives and validates JSON payload with secret. |  | pending
S03 | G01 | TradingView webhook endpoint and alert validation | S03_G01_TB002 | Map incoming alerts to internal Alert entities and persist to DB. |  | pending
S03 | G01 | TradingView webhook endpoint and alert validation | S03_G01_TB003 | Implement basic unit tests for webhook endpoint and validation. |  | pending
S03 | G02 | Alert-to-order transformation and manual queue creation | S03_G02_TB001 | Implement service to convert Alert into Order Request (manual mode by default). |  | pending
S03 | G02 | Alert-to-order transformation and manual queue creation | S03_G02_TB002 | Persist orders with WAITING status in DB for manual queue. |  | pending
S03 | G02 | Alert-to-order transformation and manual queue creation | S03_G02_TB003 | Expose API to list waiting orders and basic order details for frontend. |  | pending
S03 | G03 | Risk management placeholder for later full implementation | S03_G03_TB001 | Add pluggable Risk Engine interface with stub implementation (logs checks but does not enforce yet). |  | pending
S04 | G01 | Dashboard layout and navigation structure | S04_G01_TF001 | Implement top-level navigation items (Dashboard, Queue, Orders, Analytics, Settings). |  | pending
S04 | G01 | Dashboard layout and navigation structure | S04_G01_TF002 | Create Dashboard page skeleton with placeholder widgets (P&L, trade count, connection status). |  | pending
S04 | G02 | Waiting queue UI for manual orders | S04_G02_TF001 | Implement Waiting Queue page with Material UI table of pending orders. |  | pending
S04 | G02 | Waiting queue UI for manual orders | S04_G02_TF002 | Add inline editing for quantity, price, order type, and product fields in queue rows. |  | pending
S04 | G02 | Waiting queue UI for manual orders | S04_G02_TF003 | Wire Execute and Cancel buttons to backend APIs (no broker integration yet). |  | pending
S04 | G02 | Waiting queue UI for manual orders | S04_G02_TB004 | Implement backend APIs to update/cancel waiting orders and track status changes. |  | pending
S04 | G03 | Basic order history UI and backend API | S04_G03_TB001 | Implement backend API to list all orders with filters (date, strategy, status, symbol). |  | pending
S04 | G03 | Basic order history UI and backend API | S04_G03_TF002 | Create Orders History page with filter controls and table displaying orders. |  | pending
S05 | G01 | Integrate Zerodha Kite Connect client on backend | S05_G01_TB001 | Configure Zerodha Kite Connect Python client with API key/secret from env. |  | pending
S05 | G01 | Integrate Zerodha Kite Connect client on backend | S05_G01_TB002 | Implement service for placing market/limit orders via Zerodha API. |  | pending
S05 | G01 | Integrate Zerodha Kite Connect client on backend | S05_G01_TB003 | Implement service to fetch order book and order status from Zerodha. |  | pending
S05 | G02 | Broker connection flow (Connect Zerodha) | S05_G02_TB001 | Implement backend endpoints for Zerodha OAuth flow and token exchange. |  | pending
S05 | G02 | Broker connection flow (Connect Zerodha) | S05_G02_TB002 | Securely store encrypted Zerodha access token in DB. |  | pending
S05 | G02 | Broker connection flow (Connect Zerodha) | S05_G02_TF003 | Create frontend Connect Zerodha UI with button and status indicator. |  | pending
S05 | G03 | Send orders from manual queue to Zerodha | S05_G03_TB001 | Wire Execute action to call Zerodha order placement service and update order with broker ID. |  | pending
S05 | G03 | Send orders from manual queue to Zerodha | S05_G03_TB002 | Handle Zerodha errors and update order status to FAILED with error message. |  | pending
S05 | G03 | Send orders from manual queue to Zerodha | S05_G03_TF003 | Surface broker execution results and errors in Waiting Queue and Orders History UI. |  | pending
S06 | G01 | Implement AUTO and MANUAL execution modes per strategy | S06_G01_TB001 | Extend strategies to include execution_mode (AUTO/MANUAL) in DB and APIs. |  | pending
S06 | G01 | Implement AUTO and MANUAL execution modes per strategy | S06_G01_TB002 | Implement alert routing logic based on strategy execution_mode (AUTO -> immediate send, MANUAL -> queue). |  | pending
S06 | G01 | Implement AUTO and MANUAL execution modes per strategy | S06_G01_TF003 | Add UI controls to view and change execution mode per strategy in Settings. |  | pending
S06 | G02 | Risk management engine (limits and overrides) | S06_G02_TB001 | Implement risk rules for max_order_value, max_quantity_per_order, and allow_short_selling. |  | pending
S06 | G02 | Risk management engine (limits and overrides) | S06_G02_TB002 | Implement daily loss limit tracking and enforcement in Risk Engine. |  | pending
S06 | G02 | Risk management engine (limits and overrides) | S06_G02_TB003 | Make Risk Engine apply to both auto and manual executions before broker call. |  | pending
S06 | G02 | Risk management engine (limits and overrides) | S06_G02_TF004 | Display risk-related rejections/adjustments in UI (tooltips, messages on orders). |  | pending
S06 | G03 | Trade type (MIS/CNC) and GTT-related behavior | S06_G03_TB001 | Extend order model and APIs to handle product type (MIS/CNC) and optional GTT properties. |  | pending
S06 | G03 | Trade type (MIS/CNC) and GTT-related behavior | S06_G03_TF002 | Allow users to modify trade_type and GTT toggle in Waiting Queue UI before execution. |  | pending
S07 | G01 | Order status synchronization with Zerodha | S07_G01_TB001 | Implement background job to periodically sync order statuses from Zerodha (OPEN/COMPLETE/REJECTED). |  | pending
S07 | G01 | Order status synchronization with Zerodha | S07_G01_TB002 | Update Orders table with latest status and broker messages. |  | pending
S07 | G01 | Order status synchronization with Zerodha | S07_G01_TF003 | Reflect real-time-ish status changes in Orders History UI (polling or refresh). |  | pending
S07 | G02 | Positions and holdings view | S07_G02_TB001 | Implement backend services to fetch positions and holdings from Zerodha and cache in DB. |  | pending
S07 | G02 | Positions and holdings view | S07_G02_TB002 | Expose API endpoints for positions and holdings for frontend. |  | pending
S07 | G02 | Positions and holdings view | S07_G02_TF003 | Create Positions & Holdings UI pages with P&L calculations. |  | pending
S07 | G03 | Analytics backend for P&L and strategy performance | S07_G03_TB001 | Implement trade grouping logic (entry/exit pairs) to populate analytics_trades table. |  | pending
S07 | G03 | Analytics backend for P&L and strategy performance | S07_G03_TB002 | Implement analytics queries for P&L, win rate, max drawdown per strategy and date range. |  | pending
S07 | G03 | Analytics backend for P&L and strategy performance | S07_G03_TB003 | Expose analytics API endpoints for frontend consumption. |  | pending
S07 | G04 | Analytics frontend (charts and tables) | S07_G04_TF001 | Implement Analytics page with summary cards (P&L, win rate, max DD, avg R:R). |  | pending
S07 | G04 | Analytics frontend (charts and tables) | S07_G04_TF002 | Add P&L over time chart and P&L by symbol/strategy visualizations. |  | pending
S07 | G04 | Analytics frontend (charts and tables) | S07_G04_TF003 | Add trades table with filters for date range, strategy, and symbol. |  | pending
S08 | G01 | Structured logging, error handling, and observability | S08_G01_TB001 | Implement structured logging for backend (alerts, orders, broker calls, risk decisions). |  | pending
S08 | G01 | Structured logging, error handling, and observability | S08_G01_TB002 | Standardize error responses and add correlation IDs for tracing requests. |  | pending
S08 | G01 | Structured logging, error handling, and observability | S08_G01_TF003 | Add minimal log/notification view in UI for recent errors/warnings. |  | pending
S08 | G02 | Security hardening and configuration management | S08_G02_TB001 | Ensure HTTPS, secure cookie/JWT handling, and secret management via environment variables. |  | pending
S08 | G02 | Security hardening and configuration management | S08_G02_TB002 | Review and harden RBAC or at least basic auth protections for APIs and admin features. |  | pending
S08 | G03 | Deployment setup and documentation | S08_G03_TB001 | Create Dockerfiles for backend and frontend and optional docker-compose setup for local run. |  | pending
S08 | G03 | Deployment setup and documentation | S08_G03_TB002 | Document deployment steps (local, and optional cloud target) and operational runbook. |  | pending
S08 | G03 | Deployment setup and documentation | S08_G03_TB003 | Update README with final architecture, sprint summary, and how to operate the app. |  | pending