## README
AI Trading Manager – Engineering Implementation Plan
Generated: | 2026-02-18
Source documents:
- docs/ai_trading_manager/PRD_AI_Trading_Manager.md
- docs/ai_trading_manager/ARCH_AI_Trading_Manager.md
- docs/ai_trading_manager/PHASE_PLAN.md
- docs/ai_trading_manager/CODEX_IMPLEMENTATION_GUIDE.md
Product contract preserved:
- Assistant always-present in ST Web UI (Phase 1)
- User message = authorization for delegated execution
- Deterministic RiskGate + always-on audit trail (DecisionTrace)
- Strong idempotency + de-duplication
- Broker truth (Kite via Kite MCP) is canonical; ST keeps expected ledger + reconciliation
- Policy veto is mandatory; no override within ST
How to use this workbook:
1) Start with Roadmap + Epics.
2) Execute Phase 0 tasks behind flags; safe to merge without impacting existing order flows.
3) Use Phase sheets for sprint planning; use Backend/Frontend/DB/QA sheets for ownership.
4) Keep Status/Start Date/Due Date/Notes up to date; use Dependencies to unblock work.
Assumptions (documented to avoid blocking):
- Backend is FastAPI (backend/app/*), DB is SQLite via SQLAlchemy + Alembic (backend/alembic/*).
- Frontend is React + Vite + MUI (frontend/src/*); persistent panel is implemented in frontend/src/layouts/MainLayout.tsx.
- Kite MCP is reachable from backend via an HTTP/MCP client wrapper (implementation TBD); tokens are stored server-side only (encrypted).
- Existing Zerodha KiteConnect flows remain unchanged; AI TM uses BrokerAdapter abstraction and is fully flag-gated.
- LLM provider integration is pluggable; execution boundary remains deterministic via PlanEngine + RiskGate + ExecutionEngine.
Task columns (applies to all task sheets):
Column | Meaning
Phase | 0–3 (phase-gated).
Epic ID | E0–E6 aligned to CODEX_IMPLEMENTATION_GUIDE.
Task ID | Stable unique identifier (e.g., E3-T007).
Dependencies | Task IDs that must be completed first.
Feature Flag(s) impacted | One or more of: ai_assistant_enabled, ai_execution_enabled, kite_mcp_enabled, monitoring_enabled.
Telemetry/Audit | What to log/trace/measure for reliability + audit.
Status | Not Started / In Progress / Blocked / Done.

## Roadmap
Phase | Name | Objectives | Deliverables | Exit Criteria | Primary Flags
0 | Foundation (Reliability First) | Build audit + snapshot + reconciliation backbone. | Snapshot store; Decision/Audit store schema; Reconciler MVP; Exceptions Center (read-only); BrokerAdapter stub. | You can see broker vs ST differences consistently and clearly. | ai_assistant_enabled, kite_mcp_enabled, monitoring_enabled (disabled by default)
1 | Wow MVP | Always-present assistant + broker-aware DI + delegated execution (policy-gated). | Assistant panel; Orchestrator; KiteMCPAdapter; TradePlan generation + viewer; RiskGate v1; Execution engine (idempotent); Monitoring scheduler v1; DecisionTrace viewer. | Monitor works; Buy/Sell with constraints works; Veto works; No duplicates; Reconciliation passes for typical day. | ai_assistant_enabled, kite_mcp_enabled, ai_execution_enabled, monitoring_enabled
2 | Playbooks + Cautious Automation | Repeatable workflows and explicitly armed automations. | Playbook library; Arming model; Portfolio DI (drift/correlation/risk budgets); Exceptions remediation actions. | Armed playbooks can run safely; remediation actions are auditable and policy-gated. | monitoring_enabled, ai_execution_enabled
3 | Moat Hardening | Advanced decision intelligence while staying deterministic at execution boundary. | Regime/vol overlays; smarter sizing suggestions; additional broker adapters; deeper observability and audit hardening. | System is robust under broker/API failures and policy changes; clear operational runbooks. | monitoring_enabled

## Epics
Epic ID | Epic Name | Scope Summary | Key Deliverables | Primary Dependencies
E0 | Data & Audit Foundation | DB schema and APIs for snapshots, DecisionTrace, idempotency, monitor jobs, reconciliation deltas/exceptions. | Tables + migration; audit_store; trace/exceptions APIs; retention + redaction. | Phase 0 foundation for all epics.
E1 | Broker Adapter + Kite MCP | BrokerAdapter abstraction + Kite MCP integration for truth snapshots, quotes, and order placement. | Kite MCP adapter; token storage; snapshot ingestion; quote cache; broker-down degradation. | E0 tables + audit; E4 execution for place_order.
E2 | Reconciler + Exceptions Center | Reconciler engine and Exceptions Center for truth vs expected mismatch detection and remediation. | Reconciler MVP; severity classification; Exceptions UI; remediation actions (Phase 2). | E0 snapshots; E1 snapshots; E4 execution hooks.
E3 | RiskGate v1 | Deterministic RiskGate rules engine enforcing policy veto with reason codes. | Policy config + versioning; rule library; risk preview; veto cards; determinism tests. | E0 schemas; E1 quotes; E4 execution gating.
E4 | Execution Engine (Idempotent) | Idempotent execution engine translating plans to broker orders, handling retries, status polling, and partial fills. | IdempotencyStore; execute API; broker placement; polling; partial-fill handling; observability. | E3 RiskGate allow required; E1 adapter; E0 trace.
E5 | Assistant UI + Orchestrator | Always-present assistant UI and backend orchestrator; plan generation, action cards, trace viewer. | Assistant panel; tool router; intent parser; PlanEngine; plan viewer; action cards; trace timeline. | E0 trace APIs; E3 preview/veto; E4 execute API.
E6 | Monitoring Scheduler | Monitoring scheduler and trigger/action card flow, extending into armed automation in Phase 2. | MonitorJob CRUD; scheduler; deterministic evaluator; trigger cards; automation runner. | E1 quotes; E3 policies; E4 execution (for armed runs).

## Phase0_Foundation
Phase | Epic ID | Task ID | Title | Description | Dependencies | Owner Type | Estimated Effort | Risk | Acceptance Criteria | Expected Files/Modules | Feature Flag(s) impacted | Telemetry/Audit | Status | Start Date | Due Date | Notes
0 | E0 | E0-T001 | Define AI Trading Manager data contracts | Create the canonical DTOs/schemas used across orchestrator, RiskGate, execution, reconciliation, and monitoring to enforce stable contracts and support replayable audits. |  | BE | M | M | - Schemas exist for BrokerSnapshot, LedgerSnapshot, TradeIntent, TradePlan, DecisionTrace, IdempotencyRecord, MonitorJob, ReconciliationDelta - All schemas are versioned (v1) and validated by unit tests | backend/app/schemas/ai_trading_manager.py backend/app/schemas/__init__.py | ai_assistant_enabled | Log schema_version + correlation_id in all AI TM endpoints; store schema_version on persisted records. | Not Started
0 | E0 | E0-T002 | Add snapshot persistence models | Persist BrokerSnapshot and LedgerSnapshot as immutable snapshots to support deterministic RiskGate inputs, reconciliation, and audit replay. | E0-T001 | DB | M | M | - SQLAlchemy models for broker_snapshots and ledger_snapshots exist - Snapshots are append-only and keyed by (account_id, as_of_ts, source) | backend/app/models/ai_trading_manager_snapshots.py backend/app/models/__init__.py | kite_mcp_enabled | Audit snapshot_ingest events with snapshot_id, account_id, as_of_ts, source. | Not Started
0 | E0 | E0-T003 | Add DecisionTrace persistence models | Persist DecisionTrace as the always-on audit artifact for every AI decision and delegated action, including tool calls and outcomes. | E0-T001 | DB | M | H | - DecisionTrace tables store user_message, inputs_used snapshot references, tool calls, riskgate result, and final outcome - Every persisted trace has a stable decision_id and correlation_id | backend/app/models/ai_trading_manager_traces.py backend/app/models/__init__.py | ai_assistant_enabled | All writes emit structured log ai_tm.decision_trace.persisted with decision_id + correlation_id. | Not Started
0 | E0 | E0-T004 | Add IdempotencyRecord persistence model | Persist idempotency keys and resulting broker order IDs to guarantee at-most-once order placement across retries, refreshes, and UI resends. | E0-T001 | DB | S | H | - IdempotencyRecord table enforces unique key per scope (account_id + key) - Record stores status + broker_order_ids + first_seen_ts | backend/app/models/ai_trading_manager_idempotency.py backend/app/models/__init__.py | ai_execution_enabled | Log idempotency_hit/idempotency_miss and record latency for ExecutionEngine calls. | Not Started
0 | E0 | E0-T005 | Add MonitorJob persistence models | Persist MonitorJob definitions and trigger history to support monitoring-as-a-service and action cards. | E0-T001 | DB | M | M | - MonitorJob table stores symbols, conditions, cadence, window, enabled state - Trigger events are persisted with references back to MonitorJob and snapshots | backend/app/models/ai_trading_manager_monitoring.py backend/app/models/__init__.py | monitoring_enabled | Emit monitoring.job_created/job_triggered events with monitor_job_id + correlation_id. | Not Started
0 | E0 | E0-T006 | Add reconciliation delta and exception models | Persist ReconciliationDelta and Exceptions as first-class operational artifacts for the Exceptions Center and remediation flows. | E0-T001 | DB | M | M | - ReconciliationDelta and Exception tables store severity, classification, and references to broker/ledger snapshots - Exceptions can be acknowledged and tracked over time | backend/app/models/ai_trading_manager_reconciliation.py backend/app/models/__init__.py | ai_assistant_enabled | Emit reconciliation.delta_created and exception.opened/acknowledged events. | Not Started
0 | E0 | E0-T007 | Create Alembic migration for AI Trading Manager tables | Add a single Phase 0 migration that introduces the AI Trading Manager tables without impacting existing order flows. | E0-T002, E0-T003, E0-T004, E0-T005, E0-T006 | DB | S | M | - alembic upgrade head creates new tables successfully on SQLite - Existing migrations and tests continue to pass | backend/alembic/versions/xxxx_ai_trading_manager_foundation.py | ai_assistant_enabled | Log migration version + db schema version at app startup. | Not Started
0 | E0 | E0-T008 | Implement audit store query services | Create service-layer functions to write/read snapshots, traces, deltas, and exceptions with pagination and filters for UI consumption. | E0-T007 | BE | M | M | - Service functions support list-by-account and filter-by-time-window - All reads are bounded and paginated | backend/app/services/ai_trading_manager/audit_store.py backend/app/services/ai_trading_manager/__init__.py | ai_assistant_enabled | Trace audit_store query timings (p95) and row counts. | Not Started
0 | E0 | E0-T009 | Add correlation ID and decision ID plumbing | Ensure every AI TM request and internal action has correlation_id/decision_id for end-to-end traceability across logs, DB, and UI. | E0-T003 | BE | S | M | - FastAPI middleware attaches correlation_id to request context and response headers - DecisionTrace always includes correlation_id | backend/app/core/logging.py backend/app/services/ai_trading_manager/correlation.py | ai_assistant_enabled | Add correlation_id to all structured logs and error reports for AI TM routes. | Not Started
0 | E0 | E0-T010 | Add DecisionTrace query API endpoints | Expose read-only APIs to list and fetch DecisionTraces so the UI can show a decision timeline and allow debugging. | E0-T008, E0-T009 | BE | M | M | - GET /api/ai/decision-traces lists traces with filters (account_id, time, outcome) - GET /api/ai/decision-traces/{decision_id} returns full trace payload | backend/app/api/ai_trading_manager.py backend/app/api/routes.py | ai_assistant_enabled | Audit access to traces (who/when) and log query filter usage. | Not Started
0 | E0 | E0-T011 | Add Exceptions and reconciliation APIs | Expose APIs to list exceptions and reconciliation deltas; Phase 0 is read-only (no remediation actions executed). | E0-T008 | BE | M | M | - GET /api/ai/exceptions supports list + detail - GET /api/ai/reconciliation/deltas supports list + severity filtering | backend/app/api/ai_trading_manager.py | ai_assistant_enabled | Log exception read events and count by severity. | Not Started
0 | E0 | E0-T012 | Add retention and pruning job stub | Introduce a disabled-by-default retention job for snapshots/traces so data growth is controlled before enabling monitoring/execution. | E0-T008 | DevOps | S | L | - Retention settings exist (days) and default to no-op - Manual run prunes only AI TM tables and logs deletions | backend/app/services/ai_trading_manager/retention.py backend/app/core/config.py | monitoring_enabled | Emit retention.prune_run with deleted_row_counts per table. | Not Started
0 | E1 | E1-T001 | Define BrokerAdapter interface and DTOs | Introduce a multi-broker abstraction for snapshots, quotes, and order placement so AI TM can remain broker-agnostic while using Kite MCP first. | E0-T001 | BE | S | M | - BrokerAdapter interface exists with get_snapshot/get_quotes/place_order/get_orders/get_trades - DTOs cover Quote, OrderIntent, BrokerOrderAck and map to schemas | backend/app/services/ai_trading_manager/broker_adapter.py | kite_mcp_enabled | Log broker_adapter.selected with adapter name and account_id. | Not Started
0 | E1 | E1-T002 | Implement StubBrokerAdapter for local dev | Provide a predictable stub adapter so Phase 0 UI and pipelines can be built and tested without any broker connectivity. | E1-T001 | BE | S | L | - Stub adapter returns deterministic snapshots and quotes - Stub place_order returns a fake BrokerOrderAck and records intents for inspection | backend/app/services/ai_trading_manager/brokers/stub.py | kite_mcp_enabled | Log stub broker calls with request payload sizes. | Not Started
0 | E1 | E1-T003 | Wire BrokerAdapter selection via config and flags | Select the active broker adapter (stub vs kite_mcp) via feature flags and settings without affecting existing Zerodha KiteConnect flows. | E1-T002 | DevOps | S | M | - When kite_mcp_enabled=0, AI TM uses StubBrokerAdapter - Existing /api/zerodha endpoints remain unchanged | backend/app/core/config.py backend/app/services/ai_trading_manager/broker_factory.py | kite_mcp_enabled | Emit config.ai_tm.adapter metrics at startup. | Not Started
0 | E1 | E1-T004 | Build broker-mock harness for integration tests | Create a deterministic in-process broker mock to simulate fills, rejects, and delayed status updates for integration tests and CI. | E1-T001 | QA | M | M | - Mock supports scenarios: success, reject, partial fill, delayed completion - Integration tests can run without external broker connectivity | backend/tests/helpers/broker_mock.py backend/tests/test_ai_tm_broker_mock.py | kite_mcp_enabled | Log broker_mock scenario selection per test. | Not Started
0 | E2 | E2-T001 | Define reconciliation delta schema and severity model | Define the delta model and severity classification to drive the Exceptions Center and remediation prioritization. | E0-T001 | BE | S | M | - ReconciliationDelta includes type, severity, broker_ref, expected_ref, and human summary - Severity rules are documented and unit tested | backend/app/schemas/ai_trading_manager.py backend/app/services/ai_trading_manager/reconciliation_rules.py | ai_assistant_enabled | Emit reconciliation.severity counts per run. | Not Started
0 | E2 | E2-T002 | Implement reconciler MVP (positions/orders) | Implement a first-pass reconciler that compares broker truth snapshots to ST expected ledger snapshots and emits bounded, actionable deltas. | E2-T001, E0-T002, E0-T006, E1-T002 | BE | M | H | - Given broker+ledger snapshots, reconciler produces deterministic deltas - Deltas cover missing fills, rejected orders, and stale positions | backend/app/services/ai_trading_manager/reconciler.py | ai_assistant_enabled | Log reconciliation.run with snapshot ids, delta_count, and severity histogram. | Not Started
0 | E2 | E2-T003 | Persist reconciliation runs and open exceptions | Persist reconciliation outcomes and open exceptions for medium/high severity deltas so operations can be managed in the UI. | E2-T002, E0-T006, E0-T008 | DB | M | M | - Reconciliation runs are stored with references to snapshot ids - Exceptions open automatically for severity>=M and dedupe by (type, broker_ref) | backend/app/services/ai_trading_manager/audit_store.py backend/app/models/ai_trading_manager_reconciliation.py | ai_assistant_enabled | Emit exception.opened with exception_id + severity. | Not Started
0 | E2 | E2-T004 | Add on-demand reconciliation API | Expose an API to run reconciliation on-demand for a given account_id, returning deltas and opening exceptions as needed. | E2-T002, E0-T011 | BE | S | M | - POST /api/ai/reconcile runs reconciler and returns deltas - API is read-only with respect to broker (no broker writes) | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_reconcile_api.py | ai_assistant_enabled | Audit reconcile requests with user_id and delta_count. | Not Started
0 | E2 | E2-T005 | Build read-only Exceptions Center UI | Create the Exceptions Center UI to list and inspect exceptions produced by the reconciler, without remediation actions in Phase 0. | E0-T011 | FE | M | M | - Exceptions Center lists exceptions with severity filters - Exception detail links to related DecisionTrace when available | frontend/src/views/ExceptionsCenterPage.tsx frontend/src/services/aiTradingManager.ts | ai_assistant_enabled | Log UI navigation events to exceptions center and exception_id viewed. | Not Started
0 | E3 | E3-T001 | Define policy config format and storage | Define a policy config format (YAML/JSON) and store/load it so RiskGate evaluation is deterministic and auditable. | E0-T001 | BE | M | M | - Policy config schema exists with version and reason codes - Policy config can be loaded from file or DB and is logged in traces | backend/app/services/ai_trading_manager/policy_config.py backend/app/models/execution_policy.py | ai_execution_enabled | Audit policy config version used per evaluation. | Not Started
0 | E3 | E3-T002 | Implement deterministic RiskGate engine skeleton | Implement a pure-ish evaluator that takes (TradePlan, BrokerSnapshot, LedgerSnapshot) and returns allow/deny with reason codes. | E3-T001, E0-T001 | BE | M | H | - Same inputs produce same output (determinism test) - Outputs include allow/deny, reasons[], computed metrics | backend/app/services/ai_trading_manager/riskgate/engine.py | ai_execution_enabled | Emit riskgate.eval metrics (allow/deny counts) with policy_version. | Not Started
0 | E3 | E3-T003 | Implement core policy rules (risk limits) | Implement core policies: product constraints, max per-trade risk, daily loss cap, and max open positions. | E3-T002 | BE | M | H | - Violating policies produces deny with stable reason codes - Allow path computes risk metrics and includes them in the decision | backend/app/services/ai_trading_manager/riskgate/rules_core.py backend/tests/test_ai_tm_riskgate_core.py | ai_execution_enabled | Log riskgate.deny reason code distribution. | Not Started
0 | E3 | E3-T004 | Implement symbol and market-hours policy rules | Add allow/deny lists and market-hours/square-off rules (especially for MIS) using existing market hours utilities. | E3-T002 | BE | S | M | - Outside market hours, execution is denied with explicit reason - Symbol deny list blocks execution and proposes alternatives | backend/app/services/ai_trading_manager/riskgate/rules_market.py backend/app/core/market_hours.py | ai_execution_enabled | Audit market_hours denies including evaluated timestamp. | Not Started
0 | E3 | E3-T005 | Implement quote freshness and price sanity checks | Deny execution when quotes are stale or violate price band/liquidity sanity checks to avoid bad fills. | E1-T009, E3-T002 | BE | S | M | - Stale quotes produce deny with reason code QUOTE_STALE - Price sanity checks produce deny with reason code PRICE_SANITY_FAIL | backend/app/services/ai_trading_manager/riskgate/rules_quotes.py | ai_execution_enabled | Emit quote_stale_denies with quote_age_sec. | Not Started
0 | E3 | E3-T006 | Add RiskGate determinism and rule unit tests | Add unit tests proving determinism and correctness of individual rules to protect the execution boundary. | E3-T003, E3-T004, E3-T005 | QA | M | M | - Determinism test: same inputs -> same output across multiple runs - Rule tests cover allow and deny cases for each rule | backend/tests/test_ai_tm_riskgate_determinism.py backend/tests/test_ai_tm_riskgate_rules.py | ai_execution_enabled | N/A (tests) | Not Started
0 | E4 | E4-T001 | Define OrderIntent and plan-to-order translation contract | Define the deterministic translation boundary from TradePlan to OrderIntent[] so execution remains reproducible. | E0-T001 | BE | S | M | - OrderIntent schema covers symbol, side, qty, order_type, product, limits - Translation contract is documented and unit tested | backend/app/schemas/ai_trading_manager.py backend/app/services/ai_trading_manager/execution/translator.py | ai_execution_enabled | Log translation outputs (counts) but not sensitive values. | Not Started
0 | E4 | E4-T002 | Implement IdempotencyStore service | Implement an IdempotencyStore on top of IdempotencyRecord to prevent duplicate executions across retries and UI resends. | E0-T004, E0-T008 | BE | M | H | - IdempotencyStore supports create-or-read semantics - Concurrent calls are safe (unique constraint enforced) | backend/app/services/ai_trading_manager/execution/idempotency_store.py | ai_execution_enabled | Emit idempotency.store collisions and resolution metrics. | Not Started
0 | E4 | E4-T003 | Implement ExecutionEngine dry-run skeleton | Implement a dry-run execution path that produces DecisionTrace outputs without placing broker orders. | E4-T001, E0-T003, E4-T002 | BE | M | M | - Dry-run returns translated OrderIntent[] and a DecisionTrace - No broker calls occur in dry-run mode | backend/app/services/ai_trading_manager/execution/engine.py backend/tests/test_ai_tm_execution_dry_run.py | ai_execution_enabled | Emit execution.dry_run metrics and plan_id. | Not Started
0 | E4 | E4-T004 | Add de-duplication guardrails for repeated submits | Ensure repeated UI submissions or duplicate webhook events cannot trigger duplicate executions by enforcing idempotency keys and request hashing. | E4-T002 | BE | S | H | - Same idempotency key returns the prior result without new broker orders - Different payload with same key is rejected and audited | backend/app/services/ai_trading_manager/execution/idempotency_store.py backend/app/api/ai_trading_manager.py | ai_execution_enabled | Audit idempotency_key reuse conflicts with payload hash. | Not Started
0 | E4 | E4-T005 | Implement execution kill switch and flag gating | Gate all broker write actions behind ai_execution_enabled and add a server-side kill switch for immediate rollback. | E1-T003 | DevOps | S | H | - When ai_execution_enabled=0, execution endpoints return a safe error and place zero orders - Kill switch state is logged and visible in UI | backend/app/core/config.py frontend/src/components/ai/ExecutionStatusBanner.tsx | ai_execution_enabled | Emit execution.kill_switch state changes and blocked execution attempts. | Not Started
0 | E4 | E4-T006 | Add idempotency and dedupe integration tests | Add tests proving at-most-once behavior across retries and concurrent requests using the stub broker adapter. | E4-T004, E1-T004 | QA | M | M | - Concurrent execute calls with same key place at most one mock broker order - DecisionTrace shows stable correlation IDs across retries | backend/tests/test_ai_tm_idempotency.py | ai_execution_enabled | N/A (tests) | Not Started
0 | E5 | E5-T001 | Scaffold AI Orchestrator service and tool registry | Create the AI Orchestrator module structure and explicit tool registry so AI can reason while deterministic services decide. | E0-T001 | BE | M | M | - Orchestrator module exists with tool registry interfaces - A mock provider can run end-to-end without external LLM | backend/app/services/ai_trading_manager/orchestrator.py backend/app/services/ai_trading_manager/tools/__init__.py | ai_assistant_enabled | Audit tool invocations (tool_name, inputs_summary, duration) per decision. | Not Started
0 | E5 | E5-T002 | Add assistant messaging APIs (stub) | Add APIs to post a user message and fetch the assistant thread; Phase 0 returns stub responses and always creates a DecisionTrace. | E5-T001, E0-T010 | BE | M | M | - POST /api/ai/messages persists user message and returns assistant response - Each message creates a DecisionTrace even in stub mode | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_messages_api.py | ai_assistant_enabled | Emit ai_tm.message_received and ai_tm.response_sent events. | Not Started
0 | E5 | E5-T003 | Integrate assistant panel placeholder into MainLayout | Add the UI shell for a persistent right-side assistant panel, gated behind ai_assistant_enabled to keep Phase 0 merge-safe. |  | FE | M | M | - Assistant panel mounts in frontend/src/layouts/MainLayout.tsx - When flag off, layout and performance are unchanged | frontend/src/layouts/MainLayout.tsx frontend/src/components/ai/AssistantPanelShell.tsx | ai_assistant_enabled | Track assistant panel open/close state changes. | Not Started
0 | E5 | E5-T004 | Build basic chat UI and thread rendering | Implement basic chat UI components wired to the stub messaging APIs so the panel is end-to-end visible early. | E5-T002, E5-T003 | FE | M | M | - User can send a message and see a response in the panel - Messages are persisted/fetched via backend thread APIs | frontend/src/components/ai/AssistantPanel.tsx frontend/src/services/aiTradingManager.ts | ai_assistant_enabled | Emit UI analytics for messages sent and response latency. | Not Started
0 | E5 | E5-T005 | Scaffold DecisionTrace viewer route | Create a UI route and component skeleton to display DecisionTrace timelines fetched from backend trace APIs. | E0-T010 | FE | S | M | - DecisionTrace page loads trace by decision_id - UI handles missing/not-found traces gracefully | frontend/src/views/DecisionTracePage.tsx frontend/src/routes/AppRoutes.tsx | ai_assistant_enabled | Track trace page views with decision_id. | Not Started
0 | E6 | E6-T001 | Define MonitorJob schema and condition DSL | Define the MonitorJob and a minimal condition DSL to evaluate triggers deterministically and emit action cards. | E0-T001 | BE | M | M | - MonitorJob schema supports symbols, conditions, cadence, window - Condition DSL is versioned and validated | backend/app/schemas/ai_trading_manager.py backend/app/services/ai_trading_manager/monitoring/dsl.py | monitoring_enabled | Emit monitor.dsl.parse metrics and validation errors. | Not Started
0 | E6 | E6-T002 | Implement monitoring scheduler tick loop (disabled) | Implement a safe, bounded scheduler loop to evaluate monitor jobs; disabled by default to keep Phase 0 merge-safe. | E0-T005 | BE | M | M | - Scheduler can be started/stopped via monitoring_enabled - Work per cycle is capped to avoid long stalls | backend/app/services/ai_trading_manager/monitoring/scheduler.py | monitoring_enabled | Emit monitoring.scheduler cycle duration and job counts. | Not Started
0 | E6 | E6-T003 | Add MonitorJob CRUD APIs | Add APIs to create/update/delete/list MonitorJobs; Phase 0 stores jobs but evaluation can remain stubbed. | E6-T001, E0-T005 | BE | M | M | - CRUD endpoints exist and validate DSL - All operations create DecisionTrace entries | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_monitor_jobs_api.py | monitoring_enabled | Audit monitor job CRUD events with monitor_job_id. | Not Started

## Phase1_Wow_MVP
Phase | Epic ID | Task ID | Title | Description | Dependencies | Owner Type | Estimated Effort | Risk | Acceptance Criteria | Expected Files/Modules | Feature Flag(s) impacted | Telemetry/Audit | Status | Start Date | Due Date | Notes
1 | E0 | E0-T013 | Expand DecisionTrace fields for execution and reconciliation | Extend DecisionTrace to store RiskGate results, broker acks, status polls, and reconciliation outcomes for audit-grade replay. | E0-T003, E4-T008, E2-T006 | DB | M | M | - DecisionTrace schema includes riskgate_result, orders_submitted, reconciliation_result - Trace viewer shows these fields end-to-end | backend/app/models/ai_trading_manager_traces.py backend/alembic/versions/xxxx_ai_tm_trace विस्तार.py | ai_execution_enabled | Log decision_trace schema upgrades and migration timing. | Not Started
1 | E0 | E0-T014 | Add DecisionTrace export endpoint | Support exporting a DecisionTrace as JSON for debugging and offline review while scrubbing secrets. | E0-T010, E0-T017 | BE | S | M | - Export endpoint returns deterministic JSON for a given decision_id - Secrets/tokens are redacted in exported payload | backend/app/api/ai_trading_manager.py backend/app/services/ai_trading_manager/redaction.py | ai_assistant_enabled | Audit export events with user_id + decision_id. | Not Started
1 | E0 | E0-T015 | Add RiskGate replay harness (dry-run) | Enable re-evaluating RiskGate from stored snapshots and plans to validate determinism and diagnose veto/allow decisions. | E3-T007, E0-T010 | QA | M | M | - Replay endpoint returns identical allow/deny result for the same stored inputs - Replay is read-only and never places broker orders | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_riskgate_replay.py | ai_assistant_enabled | Log replay runs with input snapshot ids + outcome. | Not Started
1 | E1 | E1-T005 | Implement Kite MCP client wrapper | Add a thin client wrapper to call Kite MCP endpoints with retries, timeouts, and structured error mapping for stable backend behavior. | E1-T001, E0-T009 | BE | M | H | - Client supports timeouts, retry with backoff, and rate limit handling - Errors are mapped to typed exceptions with safe user-facing messages | backend/app/services/ai_trading_manager/brokers/kite_mcp_client.py | kite_mcp_enabled | Emit kite_mcp.request metrics (latency, status, retries) and correlation_id. | Not Started
1 | E1 | E1-T006 | Implement server-side Kite MCP token storage | Store Kite MCP tokens server-side only using the existing encryption utilities; frontend never receives broker credentials. | E1-T005 | DB | M | H | - Tokens are encrypted at rest (reuse backend/app/core/crypto.py) - No token fields are returned by any API responses | backend/app/models/broker.py backend/app/services/ai_trading_manager/brokers/kite_mcp_tokens.py | kite_mcp_enabled | Audit token create/refresh/revoke events without logging the token value. | Not Started
1 | E1 | E1-T007 | Add Kite MCP connect/status APIs | Expose backend APIs for initiating Kite MCP connection, checking status, and revoking tokens to support UI setup. | E1-T006 | BE | M | M | - Endpoints exist: GET status, POST connect/callback (as required), POST revoke - Status includes last_success_ts and scoped capabilities | backend/app/api/ai_broker_kite_mcp.py frontend/src/services/aiBroker.ts | kite_mcp_enabled | Emit kite_mcp.auth.status with connected=true/false and last_success_ts. | Not Started
1 | E1 | E1-T008 | Implement broker snapshot ingestion via Kite MCP | Fetch holdings/positions/orders/margins from Kite MCP and persist BrokerSnapshot for audit, reconciliation, and RiskGate inputs. | E1-T005, E0-T002 | BE | M | H | - get_snapshot returns BrokerSnapshot and persists it with snapshot_id - Snapshot ingestion is idempotent for identical as_of_ts | backend/app/services/ai_trading_manager/brokers/kite_mcp_adapter.py backend/app/services/ai_trading_manager/audit_store.py | kite_mcp_enabled | Log snapshot.fetch success/failure and snapshot freshness. | Not Started
1 | E1 | E1-T009 | Implement quotes fetch and cache via Kite MCP | Fetch quotes needed for monitoring and RiskGate checks, caching within a bounded TTL to control broker load. | E1-T005 | BE | M | M | - get_quotes returns Quote[] with as_of_ts - Quote age is exposed so RiskGate can deny stale quotes | backend/app/services/ai_trading_manager/brokers/kite_mcp_adapter.py backend/app/services/ai_trading_manager/quotes_cache.py | kite_mcp_enabled | Emit quotes.cache_hit/cache_miss and quote_age_sec distribution. | Not Started
1 | E1 | E1-T010 | Implement order placement via Kite MCP adapter | Place broker orders through Kite MCP with full correlation/idempotency context; broker remains the ultimate truth for order status. | E4-T008, E1-T005 | BE | M | H | - place_order sends OrderIntent and returns BrokerOrderAck with broker_order_id - Duplicate calls with same idempotency key do not create multiple broker orders | backend/app/services/ai_trading_manager/brokers/kite_mcp_adapter.py | ai_execution_enabled, kite_mcp_enabled | Audit order.place requests with correlation_id, idempotency_key, and broker_order_id. | Not Started
1 | E1 | E1-T011 | Implement orders/trades polling via Kite MCP | Support querying broker orders and trades for post-trade verification and reconciliation. | E1-T005 | BE | S | M | - get_orders/get_trades endpoints are wired and return normalized DTOs - Polling handles transient errors and respects rate limits | backend/app/services/ai_trading_manager/brokers/kite_mcp_adapter.py | kite_mcp_enabled | Emit broker.poll metrics (poll_count, latency, errors). | Not Started
1 | E1 | E1-T012 | Add broker-down degradation and circuit breaker | When Kite MCP is unavailable, degrade AI TM to read-only mode with explicit UI warnings and block execution. | E1-T005, E4-T005 | DevOps | M | H | - Circuit breaker opens on repeated failures and cools down automatically - Execution endpoints refuse to place orders when broker is down | backend/app/services/ai_trading_manager/brokers/circuit_breaker.py frontend/src/components/ai/BrokerStatusBanner.tsx | kite_mcp_enabled, ai_execution_enabled | Emit broker.circuit_state and broker.down incidents with duration. | Not Started
1 | E2 | E2-T006 | Schedule reconciliation after execution and on cadence | Run reconciler after each execution and on a safe cadence to ensure broker truth and expected ledger converge quickly. | E4-T009, E6-T002 | BE | M | H | - After successful execution, reconciliation runs automatically - Cadence run is bounded (max work per cycle) and can be disabled | backend/app/services/ai_trading_manager/reconciler_runner.py | monitoring_enabled | Emit reconciliation.runner metrics (runs, duration, failures). | Not Started
1 | E2 | E2-T007 | Implement post-trade verification polling | Poll broker order status until a terminal state or timeout, then reconcile; ensures partial fills and delayed completion are handled safely. | E1-T011, E4-T008 | BE | M | H | - Execution flow polls until COMPLETE/REJECTED/CANCELLED or timeout - Timeout produces an exception with actionable next steps | backend/app/services/ai_trading_manager/post_trade_verifier.py backend/tests/test_ai_tm_post_trade_verifier.py | ai_execution_enabled | Emit post_trade.verify metrics (polls, timeout_rate). | Not Started
1 | E2 | E2-T008 | Add exception detail view with trace linkage | Enhance Exceptions Center with a detail view that links to DecisionTrace and shows broker vs expected diffs. | E2-T005, E5-T012 | FE | M | M | - Exception detail shows delta breakdown and related broker ids - One-click navigation to DecisionTrace viewer works | frontend/src/views/ExceptionsCenterPage.tsx frontend/src/views/DecisionTracePage.tsx | ai_assistant_enabled | Track exception detail views and trace open actions. | Not Started
1 | E2 | E2-T009 | Add exception action stubs (ack/snooze) | Implement non-trading exception actions (acknowledge/snooze) to manage noise while keeping remediation execution for Phase 2. | E0-T011 | BE | S | L | - POST /api/ai/exceptions/{id}/ack updates state and writes audit log - UI updates immediately and shows acknowledged state | backend/app/api/ai_trading_manager.py frontend/src/views/ExceptionsCenterPage.tsx | ai_assistant_enabled | Audit exception.ack events with user_id and reason (optional). | Not Started
1 | E3 | E3-T007 | Integrate RiskGate into plan→execute pipeline | Ensure every delegated execution runs RiskGate and is vetoed deterministically when any policy fails. | E3-T006, E5-T009, E4-T012 | BE | M | H | - Execution API refuses to place orders when RiskGate returns deny - DecisionTrace stores full RiskGate input references and result | backend/app/services/ai_trading_manager/orchestrator.py backend/app/services/ai_trading_manager/riskgate/engine.py | ai_execution_enabled | Emit riskgate.veto events with reason codes and decision_id. | Not Started
1 | E3 | E3-T008 | Render policy veto reason codes in UI | Show a clear veto card that maps deterministic reason codes to actionable explanations; no override is offered inside ST. | E3-T007, E5-T011 | FE | S | M | - UI shows deny reasons and suggested adjustments - UI does not provide any 'override' action for a veto | frontend/src/components/ai/VetoCard.tsx frontend/src/components/ai/reasonCodeCopy.ts | ai_execution_enabled | Track veto card impressions and reasons shown. | Not Started
1 | E3 | E3-T009 | Add risk preview API (no execution) | Add an endpoint to evaluate RiskGate for a proposed TradePlan without placing orders, used by Plan Viewer and remediation flows. | E3-T007 | BE | S | M | - POST /api/ai/risk/preview returns RiskDecision for a plan - Preview creates a DecisionTrace marked as PREVIEW only | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_risk_preview.py | ai_execution_enabled | Emit risk.preview metrics and veto reason distribution. | Not Started
1 | E3 | E3-T010 | Compute and log risk metrics | Compute portfolio exposure metrics (concentration, leverage, open positions) and record them in RiskDecision for explainability. | E3-T007 | BE | M | M | - RiskDecision includes computed metrics - Metrics appear in DecisionTrace viewer | backend/app/services/ai_trading_manager/riskgate/metrics.py frontend/src/views/DecisionTracePage.tsx | ai_execution_enabled | Emit risk.metrics distributions (exposure, leverage) for monitoring. | Not Started
1 | E3 | E3-T011 | Enforce no-override policy for AI execution | Ensure there is no internal override path for AI delegated execution; policy veto is mandatory and cannot be bypassed within ST. | E3-T007 | QA | S | H | - Attempting to call execution endpoints without RiskGate allow returns 403/deny - Frontend does not render any override controls for vetoed trades | backend/tests/test_ai_tm_no_override.py frontend/src/components/ai/VetoCard.tsx | ai_execution_enabled | N/A (tests) | Not Started
1 | E4 | E4-T007 | Implement plan-to-order translation for core order types | Translate TradePlan into broker-ready OrderIntent for common market/limit orders while preserving determinism. | E4-T001, E5-T009 | BE | M | M | - Translator supports BUY/SELL for MIS/CNC and market/limit skeleton - Unit tests cover translation edge cases and rounding | backend/app/services/ai_trading_manager/execution/translator.py backend/tests/test_ai_tm_translator.py | ai_execution_enabled | Log translation warnings (e.g., rounding adjustments). | Not Started
1 | E4 | E4-T008 | Implement broker order placement with idempotency | Place orders via BrokerAdapter only after RiskGate allow, using idempotency and correlation IDs to ensure safety. | E3-T007, E4-T002, E1-T010 | BE | L | H | - Given same idempotency_key, no more than one broker order is placed - DecisionTrace stores request/response for each broker order | backend/app/services/ai_trading_manager/execution/engine.py | ai_execution_enabled, kite_mcp_enabled | Emit execution.order_place metrics (success/failure, retries). | Not Started
1 | E4 | E4-T009 | Implement status polling and terminal state handling | Poll broker order status for placed orders and update DecisionTrace and expected ledger state without assuming immediate completion. | E1-T011, E4-T008 | BE | M | H | - Engine detects terminal states and records them - Non-terminal states result in bounded polling then exception | backend/app/services/ai_trading_manager/execution/status_poller.py | ai_execution_enabled | Emit execution.status_poll metrics and timeout count. | Not Started
1 | E4 | E4-T010 | Handle partial fills safely | Track partial fills and ensure no duplicate follow-up orders are placed; reconciliation must surface partial-fill exceptions when needed. | E4-T009, E2-T007 | BE | M | H | - Partial fills are detected and recorded in DecisionTrace - Reconciler emits partial-fill delta and exception when applicable | backend/app/services/ai_trading_manager/execution/fills.py backend/app/services/ai_trading_manager/reconciliation_rules.py | ai_execution_enabled | Emit execution.partial_fill events with filled_qty and remaining_qty. | Not Started
1 | E4 | E4-T011 | Enforce execute-on-instruction semantics | Ensure trades are executed only when the user message is an explicit instruction; monitoring triggers and suggestions never auto-execute in Phase 1. | E5-T013 | QA | S | H | - Suggested plans do not execute without a user instruction message - Execution endpoints require an authorization_message_id | backend/tests/test_ai_tm_execute_on_instruction.py backend/app/services/ai_trading_manager/orchestrator.py | ai_execution_enabled | N/A (tests) | Not Started
1 | E4 | E4-T012 | Implement execute API endpoint | Expose the backend execution endpoint that takes plan_id + idempotency_key + authorization message reference and returns an execution outcome. | E4-T003, E4-T008 | BE | M | H | - POST /api/ai/execute validates plan, runs RiskGate, and executes only on allow - Endpoint is gated by ai_execution_enabled and records DecisionTrace | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_execute_api.py | ai_execution_enabled | Audit execute attempts with outcome allow/deny/error and correlation_id. | Not Started
1 | E4 | E4-T013 | Add broker integration tests for execution scenarios | Add integration tests using broker-mock harness for rejected orders, delayed completion, and partial fills. | E4-T012, E1-T004 | QA | M | M | - Tests cover reject, delayed status, partial fill scenarios - No test places real broker orders | backend/tests/test_ai_tm_execution_integration.py | ai_execution_enabled | N/A (tests) | Not Started
1 | E4 | E4-T014 | Add execution observability (metrics + structured logs) | Add metrics for retries, failures, veto rates, and broker latency to prioritize boring reliability. | E4-T012, E0-T009 | DevOps | S | M | - Metrics emitted for execute latency and error rate - Logs include correlation_id and idempotency_key | backend/app/services/ai_trading_manager/metrics.py backend/app/core/logging.py | monitoring_enabled | Emit execution metrics with labels: broker, outcome, retry_count. | Not Started
1 | E5 | E5-T006 | Implement assistant panel always-present UX | Deliver the Phase 1 contract: assistant is always-present in the ST Web UI (persistent panel) with a clear collapsed state. | E5-T004 | FE | M | M | - Panel persists across routes and does not unmount on navigation - Collapsed state preserves unread indicators/action cards | frontend/src/layouts/MainLayout.tsx frontend/src/components/ai/AssistantPanel.tsx | ai_assistant_enabled | Track panel persistence bugs via UI error reporting. | Not Started
1 | E5 | E5-T007 | Implement tool router with explicit scopes | Implement tool routing in the orchestrator with explicit scope checks and auditing for ST tools and broker tools. | E5-T001, E1-T001 | BE | M | H | - Each tool call is logged with scope and parameters summary - Unauthorized tools are blocked and recorded in DecisionTrace | backend/app/services/ai_trading_manager/tool_router.py backend/app/services/ai_trading_manager/tools/*.py | ai_assistant_enabled | Emit tool_router.denied metrics and tool latency histograms. | Not Started
1 | E5 | E5-T008 | Implement intent parsing to TradeIntent | Parse user messages into a TradeIntent structure; combine LLM extraction with deterministic validation and fallback parsing. | E5-T002, E0-T001 | BE | M | H | - TradeIntent extraction validates symbols/side/product/constraints - Invalid intents return a clarifying question instead of executing | backend/app/services/ai_trading_manager/intent_parser.py backend/tests/test_ai_tm_intent_parser.py | ai_assistant_enabled | Emit intent.parse success/failure counts with reason categories. | Not Started
1 | E5 | E5-T009 | Implement deterministic PlanEngine normalization | Normalize and validate TradePlan/MonitorPlan structures deterministically so execution boundary is stable even if LLM output varies. | E5-T008, E0-T001 | BE | M | H | - PlanEngine rejects invalid plans with explicit errors - Normalized plans are stable (ordering, defaults, ids) for same input | backend/app/services/ai_trading_manager/plan_engine.py backend/tests/test_ai_tm_plan_engine.py | ai_assistant_enabled | Emit plan_engine.validation_error counts and plan_normalization timings. | Not Started
1 | E5 | E5-T010 | Build Plan Viewer UI | Render TradePlan details, normalized structure, and risk preview in a dedicated viewer and in action cards. | E5-T005, E3-T009 | FE | M | M | - Plan Viewer shows plan summary + raw JSON with copy/download - Risk preview results are displayed next to the plan | frontend/src/components/ai/PlanViewer.tsx frontend/src/services/aiTradingManager.ts | ai_assistant_enabled | Track plan viewer opens and risk preview latency. | Not Started
1 | E5 | E5-T011 | Implement Action Cards UI framework | Implement the Action Card framework (monitor, execute, veto, reconcile) so assistant can propose structured actions with trace links. | E5-T006 | FE | M | M | - Cards render consistently and support primary/secondary actions - Cards link to DecisionTrace and plan viewer | frontend/src/components/ai/ActionCards.tsx frontend/src/components/ai/cards/*.tsx | ai_assistant_enabled | Track card impressions and action clicks. | Not Started
1 | E5 | E5-T012 | Implement DecisionTrace viewer timeline | Implement a DecisionTrace timeline view: inputs → tools → RiskGate → orders → reconciliation, with filters and drilldowns. | E5-T005, E0-T010 | FE | M | M | - Timeline shows tool calls and risk decisions in order - Viewer links broker_order_ids to exception details when present | frontend/src/views/DecisionTracePage.tsx frontend/src/components/ai/TraceTimeline.tsx | ai_assistant_enabled | Track trace viewer load time and error rates. | Not Started
1 | E5 | E5-T013 | Implement message-as-authorization contract | Treat an explicit user message as authorization for delegated execution, without additional per-order confirmations, while still policy-gated. | E5-T002, E4-T012 | BE | M | H | - Execution requires authorization_message_id referencing the user message - DecisionTrace stores the exact user message used for authorization | backend/app/services/ai_trading_manager/orchestrator.py backend/app/schemas/ai_trading_manager.py | ai_execution_enabled | Audit authorization usage with message_id + decision_id. | Not Started
1 | E5 | E5-T014 | Add assistant navigation to Exceptions Center | Add assistant shortcuts to open Exceptions Center and filtered views tied to current decisions. | E2-T005, E5-T011 | FE | S | L | - Action card can open Exceptions Center with prefilled filters - Exceptions Center can navigate back to related trace | frontend/src/components/ai/ActionCards.tsx frontend/src/routes/AppRoutes.tsx | ai_assistant_enabled | Track navigation from assistant to exceptions center. | Not Started
1 | E5 | E5-T015 | Add frontend feature flags for AI TM | Implement ai_assistant_enabled/ai_execution_enabled/kite_mcp_enabled/monitoring_enabled UI gating via query params and local storage. |  | FE | S | L | - Flags can be toggled via URL params for dev - UI hides AI TM features when flags are off | frontend/src/config/aiFeatures.ts frontend/src/App.tsx | ai_assistant_enabled, ai_execution_enabled, kite_mcp_enabled, monitoring_enabled | Track feature flag states in client-side diagnostics logs. | Not Started
1 | E6 | E6-T004 | Implement deterministic condition evaluator | Evaluate monitor job conditions using quotes + portfolio state deterministically, producing triggers with reason details. | E1-T009, E6-T001 | BE | M | M | - Evaluator returns same result for same inputs - Evaluator records inputs_used in DecisionTrace | backend/app/services/ai_trading_manager/monitoring/evaluator.py backend/tests/test_ai_tm_monitor_evaluator.py | monitoring_enabled | Emit monitoring.eval metrics and trigger counts. | Not Started
1 | E6 | E6-T005 | Run monitor jobs on cadence and persist triggers | Run monitor jobs on schedule, persist trigger events, and push action cards to the assistant thread. | E6-T002, E6-T004, E0-T005 | BE | M | M | - Scheduler computes next_run_ts and persists last_run_ts - Triggers are persisted and deduped per (job, window) | backend/app/services/ai_trading_manager/monitoring/scheduler.py backend/app/services/ai_trading_manager/monitoring/store.py | monitoring_enabled | Emit monitoring.job_run metrics and trigger_dedupe hits. | Not Started
1 | E6 | E6-T006 | Render trigger action cards in assistant UI | Display monitoring triggers as assistant action cards with quick actions (view details, propose plan, acknowledge). | E5-T011, E6-T005 | FE | M | M | - Trigger cards appear in assistant panel with timestamps - Cards link to monitor job and decision trace | frontend/src/components/ai/cards/MonitorTriggerCard.tsx | monitoring_enabled | Track trigger card impressions and acknowledgements. | Not Started
1 | E6 | E6-T007 | Integrate execute-on-instruction from triggers | When a trigger fires, assistant proposes a plan; execution occurs only when user explicitly instructs (message = authorization). | E6-T006, E4-T011 | BE | M | H | - Trigger flow creates a proposed plan and risk preview - No auto-execution occurs without explicit authorization message | backend/app/services/ai_trading_manager/orchestrator.py frontend/src/components/ai/cards/MonitorTriggerCard.tsx | monitoring_enabled, ai_execution_enabled | Audit trigger→plan proposals with monitor_job_id and decision_id. | Not Started
1 | E6 | E6-T008 | Add monitoring telemetry and failure handling | Add metrics and robust failure handling for the scheduler (per-job errors, retries, backoff) to avoid noisy loops. | E6-T005 | DevOps | S | M | - Scheduler logs failures per job and backs off - Metrics include job failure rate and mean run duration | backend/app/services/ai_trading_manager/monitoring/scheduler.py backend/app/services/ai_trading_manager/metrics.py | monitoring_enabled | Emit monitoring.scheduler.failure metrics and backoff state. | Not Started

## Phase2_Playbooks_Automation
Phase | Epic ID | Task ID | Title | Description | Dependencies | Owner Type | Estimated Effort | Risk | Acceptance Criteria | Expected Files/Modules | Feature Flag(s) impacted | Telemetry/Audit | Status | Start Date | Due Date | Notes
2 | E0 | E0-T016 | Add playbook lifecycle audit events | Extend audit model to capture playbook creation, edits, arming/unarming, and runs with stable linking to DecisionTraces. | E5-T016 | BE | M | M | - Playbook actions create DecisionTrace entries with action_type=PLAYBOOK_* - UI can filter traces by playbook_id | backend/app/models/ai_trading_manager_traces.py backend/app/services/ai_trading_manager/audit_store.py | monitoring_enabled | Emit playbook.audit events with playbook_id + armed_state. | Not Started
2 | E0 | E0-T017 | Implement trace redaction and secret scrubbing | Prevent leakage of broker tokens, API keys, and PII into DecisionTrace storage and exports. | E1-T006, E0-T003 | BE | S | H | - All tokens/secrets are stored only in server-side secret tables - Trace payloads are scrubbed before persistence and export | backend/app/services/ai_trading_manager/redaction.py backend/tests/test_ai_tm_redaction.py | ai_assistant_enabled | Log redaction hits count and redact types (token/key/PII). | Not Started
2 | E1 | E1-T013 | Implement broker rate-limit budgeting | Coordinate broker API usage across monitoring, reconciliation, and execution using a shared budget to prevent throttling. | E6-T005, E1-T009 | BE | M | M | - Shared rate limiter enforces max requests/sec - Monitoring backs off automatically when budget is exhausted | backend/app/services/ai_trading_manager/brokers/rate_limit.py | monitoring_enabled, kite_mcp_enabled | Emit broker.rate_limit.throttles and per-component request counts. | Not Started
2 | E1 | E1-T014 | Add multi-account broker partitioning | Support account_id scoping across snapshots, idempotency, and monitor jobs to prepare for multi-account use. | E0-T007 | DB | M | M | - All AI TM tables are partitioned by account_id - APIs require account_id and enforce isolation | backend/app/models/ai_trading_manager_*.py backend/app/api/ai_trading_manager.py | ai_assistant_enabled | Log account_id on all AI TM actions and enforce access checks. | Not Started
2 | E2 | E2-T010 | Implement remediation: resync expected ledger from broker truth | Add a safe remediation action to rebuild ST expected ledger state from broker truth snapshots, with full audit and guardrails. | E2-T006, E0-T002 | BE | M | H | - Resync is read-only w.r.t broker and only updates expected ledger - DecisionTrace records before/after snapshots and action outcome | backend/app/services/ai_trading_manager/remediation.py backend/app/api/ai_trading_manager.py | ai_assistant_enabled | Emit remediation.resync events with affected entity counts. | Not Started
2 | E2 | E2-T011 | Implement remediation: retry execution with safeguards | Allow retrying a failed execution via Exceptions Center using a new idempotency key, after re-running RiskGate and policy checks. | E4-T012, E3-T009 | BE | M | H | - Retry requires explicit user instruction (message = authorization) - RiskGate is re-evaluated and can veto the retry | backend/app/services/ai_trading_manager/remediation.py frontend/src/components/ai/ActionCards.tsx | ai_execution_enabled | Audit remediation.retry with original decision_id and new decision_id. | Not Started
2 | E2 | E2-T012 | Add remediation suggestions (close/hedge proposals) | Generate deterministic remediation suggestions for risky exceptions (e.g., approaching MIS square-off) as action cards; execution still requires instruction/arming. | E6-T012, E3-T004 | FE | M | M | - UI shows remediation suggestion cards with clear rationale - No broker orders are placed unless user instructs and policy allows | frontend/src/components/ai/RemediationCards.tsx backend/app/services/ai_trading_manager/remediation_suggestions.py | ai_assistant_enabled | Track suggestion impressions and user follow-through. | Not Started
2 | E2 | E2-T013 | Detect manual broker trades and expected-ledger drift | Classify deltas caused by manual broker actions and surface them as drift exceptions with clear remediation options. | E1-T008, E2-T002 | BE | M | M | - Reconciler labels drift vs ST-caused mismatches - Exceptions Center shows 'manual broker trade detected' with details | backend/app/services/ai_trading_manager/reconciliation_rules.py frontend/src/views/ExceptionsCenterPage.tsx | ai_assistant_enabled | Emit drift.detected events and counts per day. | Not Started
2 | E3 | E3-T012 | Add playbook-specific RiskGate rules | Add policies for armed playbooks: max frequency, allowed windows, and explicit arming requirement. | E6-T009, E3-T007 | BE | M | M | - Unarmed playbooks are denied with reason code PLAYBOOK_NOT_ARMED - Frequency limits deny when exceeded and produce deterministic reason | backend/app/services/ai_trading_manager/riskgate/rules_playbooks.py | monitoring_enabled | Emit playbook.riskgate denies with playbook_id. | Not Started
2 | E3 | E3-T013 | Add portfolio risk budgets and correlation constraints | Introduce portfolio-level risk budgets and correlation constraints; enforce as policy where feasible and record as advisory otherwise. | E5-T018, E3-T010 | BE | L | M | - RiskGate can deny when budgets are exceeded (configurable) - DecisionTrace stores budget inputs and computed correlation metrics | backend/app/services/ai_trading_manager/riskgate/rules_portfolio.py backend/app/services/risk_unified_store.py | ai_execution_enabled | Emit portfolio_budget metrics and deny rate. | Not Started
2 | E3 | E3-T014 | Add policy versioning and pin evaluations to version | Version policies and record which version was used for each decision so replay is accurate over time. | E3-T001, E0-T003 | DB | M | M | - Policy versions are immutable and selectable - DecisionTrace stores policy_version and config hash | backend/app/models/execution_policy.py backend/app/services/ai_trading_manager/policy_config.py | ai_execution_enabled | Audit policy.version_used per decision. | Not Started
2 | E4 | E4-T015 | Implement safe sequencing for bracket/SL orders | Add deterministic sequencing for multi-leg executions (entry + stop-loss) with safe abort behavior. | E4-T008, E3-T003 | BE | L | H | - Multi-leg execution is idempotent per leg - If any leg fails, system stops and opens an exception | backend/app/services/ai_trading_manager/execution/sequencer.py | ai_execution_enabled | Emit execution.sequence events per leg with outcome. | Not Started
2 | E4 | E4-T016 | Implement expected ledger update saga | Update ST expected ledger as a durable saga around execution steps, then reconcile against broker truth to converge. | E2-T006, E0-T002 | DB | L | H | - Expected ledger updates are transactional and replayable - Reconciler detects divergence and opens exceptions | backend/app/services/ai_trading_manager/ledger.py backend/app/models/ai_trading_manager_snapshots.py | ai_execution_enabled | Emit ledger.expected_update events with entity counts. | Not Started
2 | E4 | E4-T017 | Support execution resume after interruptions | Allow resuming an interrupted execution from stored idempotency state without placing duplicate orders. | E4-T002, E4-T009 | BE | M | H | - Restarting the backend does not lose execution state - Resume continues polling and reconciliation safely | backend/app/services/ai_trading_manager/execution/engine.py backend/tests/test_ai_tm_execution_resume.py | ai_execution_enabled | Emit execution.resume events with prior broker_order_ids. | Not Started
2 | E5 | E5-T016 | Build playbook library UI | Implement UI to save, edit, and run playbooks (saved intents/plans) as reusable workflows. | E5-T010 | FE | L | M | - User can save a plan as a playbook and list playbooks - Running a playbook creates a DecisionTrace and action cards | frontend/src/views/PlaybooksPage.tsx frontend/src/services/aiTradingManager.ts | monitoring_enabled | Track playbook create/edit/run events. | Not Started
2 | E5 | E5-T017 | Implement arming UX for playbooks | Implement explicit arming/unarming flow for automations with clear safety messaging and kill switch visibility. | E6-T009, E5-T016 | FE | M | H | - Arming requires explicit user action and is clearly indicated - UI shows when kill switch disables automation | frontend/src/components/ai/PlaybookArmingDialog.tsx | monitoring_enabled | Audit arming toggles (playbook_id, user_id) via backend. | Not Started
2 | E5 | E5-T018 | Add portfolio decision intelligence views | Add views for drift, correlation, and risk budgets that inform suggestions while keeping execution deterministic and policy-gated. | E3-T010 | FE | L | M | - Dashboard cards show drift/correlation summaries - Data sources and as_of timestamps are shown for transparency | frontend/src/views/PortfolioDIPanel.tsx frontend/src/services/analytics.ts | ai_assistant_enabled | Track DI view usage and load times. | Not Started
2 | E5 | E5-T019 | Link playbook runs to traces and exceptions | Ensure playbook runs link to DecisionTrace and any resulting exceptions for review and debugging. | E0-T016, E2-T010 | BE | S | M | - Playbook run creates trace with playbook_id - Exceptions show originating playbook when applicable | backend/app/services/ai_trading_manager/orchestrator.py backend/app/models/ai_trading_manager_reconciliation.py | monitoring_enabled | Emit playbook.run.trace_linked events. | Not Started
2 | E6 | E6-T009 | Implement playbook arming model (backend) | Persist arming state and enforce explicit enablement before any automation can execute. | E5-T016, E3-T012 | DB | M | H | - Playbook armed_state is persisted and audited - Automation runner refuses to execute unarmed playbooks | backend/app/models/ai_trading_manager_playbooks.py backend/alembic/versions/xxxx_ai_tm_playbooks.py | monitoring_enabled | Audit playbook.armed_state changes with user_id. | Not Started
2 | E6 | E6-T010 | Implement cautious automation runner | Execute only armed playbooks through the same RiskGate/ExecutionEngine pipeline, respecting kill switch and idempotency. | E6-T009, E4-T012 | BE | L | H | - Automation runs create DecisionTrace entries and are fully auditable - Kill switch disables automation immediately and stops new runs | backend/app/services/ai_trading_manager/automation/runner.py backend/tests/test_ai_tm_automation_runner.py | monitoring_enabled, ai_execution_enabled | Emit automation.run metrics and veto rates. | Not Started
2 | E6 | E6-T011 | Add monitor job backtesting/simulation mode | Allow simulating monitor jobs over historical quote data to validate conditions and reduce false triggers. | E6-T004 | BE | M | M | - Simulation produces deterministic trigger timelines - Simulation never places orders and is clearly labeled | backend/app/services/ai_trading_manager/monitoring/simulator.py frontend/src/views/MonitorJobSimPage.tsx | monitoring_enabled | Emit simulation.run metrics and duration. | Not Started
2 | E6 | E6-T012 | Add portfolio-level monitors and trigger cards | Add monitors for portfolio drawdown, drift, and concentration, emitting action cards and remediation suggestions. | E5-T018, E6-T005 | BE | L | M | - Portfolio monitors compute metrics deterministically - Trigger cards show metric deltas and as_of timestamps | backend/app/services/ai_trading_manager/monitoring/portfolio_monitors.py frontend/src/components/ai/cards/PortfolioMonitorCard.tsx | monitoring_enabled | Emit portfolio_monitor triggers and metric distributions. | Not Started

## Phase3_Moat_Hardening
Phase | Epic ID | Task ID | Title | Description | Dependencies | Owner Type | Estimated Effort | Risk | Acceptance Criteria | Expected Files/Modules | Feature Flag(s) impacted | Telemetry/Audit | Status | Start Date | Due Date | Notes
3 | E0 | E0-T018 | Add trace archival and configurable retention | Add configurable retention windows and optional archival/compression to keep audit data manageable while preserving required history. | E0-T012 | DevOps | M | M | - Retention window can be configured via env/DB settings - Archival job compresses older traces and keeps indexable metadata | backend/app/services/ai_trading_manager/retention.py backend/app/core/config.py | monitoring_enabled | Emit retention.archive_run metrics and failures. | Not Started
3 | E0 | E0-T019 | Add tamper-evident audit hashing | Add optional hash chaining across DecisionTraces to provide tamper evidence for the audit trail. | E0-T003 | BE | M | M | - Each DecisionTrace stores prev_hash and content_hash - Verifier detects any edited/deleted traces in a chain | backend/app/services/ai_trading_manager/audit_hashing.py backend/tests/test_ai_tm_audit_hashing.py | ai_assistant_enabled | Log audit_hash.verify results and mismatches. | Not Started
3 | E0 | E0-T020 | Publish audit coverage metrics | Expose metrics ensuring every AI action has a DecisionTrace and reconciliation record, enabling reliability-focused monitoring. | E0-T009, E2-T006 | DevOps | S | L | - Metrics expose counts for decisions without traces (should be 0) - Dashboard-ready metrics exist for veto rate, execution success rate, reconciliation OK rate | backend/app/api/system_events.py backend/app/services/ai_trading_manager/metrics.py | monitoring_enabled | Emit ai_tm.metrics snapshot on schedule and at startup. | Not Started
3 | E1 | E1-T015 | Add second broker adapter skeleton | Add a non-functional adapter skeleton (no execution) for a second broker to validate the abstraction and future roadmap. | E1-T001 | BE | S | L | - Adapter compiles and is selectable but returns NOT_IMPLEMENTED - Interface contract tests cover adapter behavior | backend/app/services/ai_trading_manager/brokers/angelone_mcp_adapter.py backend/tests/test_ai_tm_broker_adapter_contract.py | kite_mcp_enabled | Log adapter capability matrix at startup. | Not Started
3 | E1 | E1-T016 | Add broker capability discovery and contract tests | Add adapter capability discovery and contract tests to detect breaking changes in MCP endpoints early. | E1-T005 | QA | M | M | - Contract tests validate required fields and error mapping - CI can run against broker-mock and optionally against real MCP in staging | backend/tests/test_ai_tm_kite_mcp_contract.py | kite_mcp_enabled | Emit contract_test results as system events. | Not Started
3 | E1 | E1-T017 | Normalize broker instrument identifiers | Ensure reconciliation and quotes use a consistent symbol/instrument mapping across broker responses and ST internal keys. | E2-T002, E1-T008 | BE | M | M | - Mapping layer converts broker instrument ids to ST symbol keys - Reconciler uses mapped keys and reports mismatches clearly | backend/app/services/ai_trading_manager/symbol_mapping.py frontend/src/utils/symbolKey.ts | kite_mcp_enabled | Log symbol_mapping misses and unknown instrument ids. | Not Started
3 | E2 | E2-T014 | Optimize reconciliation with incremental diffs | Improve reconciler performance by diffing from prior runs and only evaluating changed broker/ledger entities. | E2-T006 | BE | M | M | - Reconciliation uses previous run cache when available - p95 reconciliation duration improves and is tracked | backend/app/services/ai_trading_manager/reconciler.py | monitoring_enabled | Emit reconciliation.duration p50/p95 and cache_hit ratio. | Not Started
3 | E2 | E2-T015 | Add anomaly alerts on reconciliation deltas | Detect spikes in exceptions/deltas and raise system events so operational issues are visible quickly. | E0-T020 | DevOps | S | M | - Alert triggers when exception rate exceeds threshold - Alerts link to Exceptions Center filters | backend/app/services/ai_trading_manager/anomaly_alerts.py frontend/src/services/systemEvents.ts | monitoring_enabled | Emit anomaly.alert events with thresholds and current rates. | Not Started
3 | E2 | E2-T016 | Document ledger rebuild runbook | Write an operator runbook for rebuilding expected ledger from broker truth, including rollback strategy and audit requirements. | E2-T010 | QA | S | L | - Runbook exists with step-by-step commands and verification steps - Rollback plan is included | docs/ai_trading_manager/runbooks/ledger_rebuild.md | monitoring_enabled | N/A (documentation) | Not Started
3 | E3 | E3-T015 | Add policy snapshot tests | Add snapshot tests for representative policies to detect unintended changes in rule behavior. | E3-T014 | QA | M | L | - Snapshot tests cover common allow/deny scenarios - CI fails on unexpected policy behavior changes | backend/tests/test_ai_tm_policy_snapshots.py | ai_execution_enabled | N/A (tests) | Not Started
3 | E3 | E3-T016 | Build policy editor UI (admin-only) | Provide an admin-only UI for editing policy configs safely, with validation and preview. | E3-T014, E3-T009 | FE | L | M | - Editor validates schema and shows preview results - Changes are versioned and require explicit publish step | frontend/src/views/PolicyEditorPage.tsx frontend/src/services/aiTradingManager.ts | ai_execution_enabled | Audit policy edit/publish events with user_id. | Not Started
3 | E3 | E3-T017 | Unify reason codes with existing risk engine | Map AI TM RiskGate reason codes to existing risk engine reason taxonomy so UX and reporting are consistent. | E3-T003 | BE | M | M | - Common reason code mapping is documented and implemented - Frontend displays consistent copy across order flows | backend/app/services/managed_risk.py frontend/src/services/riskEngine.ts | ai_execution_enabled | Track reason code mapping misses. | Not Started
3 | E3 | E3-T018 | Add policy change safety checklist | Create a checklist and guardrails for policy changes (testing, rollout, monitoring) to reduce operational risk. | E3-T016 | DevOps | S | L | - Checklist exists and is referenced in Release_Checklists - Policy publish flow requires running preview tests | docs/ai_trading_manager/policy_change_checklist.md | monitoring_enabled | N/A (process) | Not Started
3 | E4 | E4-T018 | Add per-symbol/account concurrency locks | Prevent overlapping executions for the same symbol/account to reduce race conditions and reconciliation churn. | E4-T008 | BE | M | M | - Concurrent execute attempts for same symbol/account are serialized - Locks are bounded and released on failures/timeouts | backend/app/services/ai_trading_manager/execution/locks.py | ai_execution_enabled | Emit execution.lock contention metrics. | Not Started
3 | E4 | E4-T019 | Add chaos tests for broker timeouts | Add chaos-style tests simulating broker timeouts and flaky responses to validate idempotency and recovery behavior. | E1-T004, E4-T017 | QA | M | M | - Chaos tests demonstrate no duplicate orders - Exceptions are opened with actionable remediation | backend/tests/test_ai_tm_execution_chaos.py | ai_execution_enabled | N/A (tests) | Not Started
3 | E4 | E4-T020 | Generate audit-grade execution report | Generate a human-readable execution report (inputs, policies, orders, outcomes) derived from DecisionTrace for post-mortem and review. | E0-T013 | FE | M | L | - Report view renders from DecisionTrace deterministically - Report includes riskgate result, broker order ids, reconciliation outcome | frontend/src/views/DecisionTracePage.tsx frontend/src/components/ai/ExecutionReport.tsx | ai_assistant_enabled | Track report views and export actions. | Not Started
3 | E5 | E5-T020 | Add regime and volatility overlay cards | Add advisory-only regime/volatility overlays to inform decisions while keeping execution boundary deterministic and policy-gated. | E5-T018 | FE | M | L | - Overlay cards clearly marked as advisory - No automated execution is triggered by overlays | frontend/src/components/ai/RegimeOverlayCard.tsx | ai_assistant_enabled | Track overlay card impressions. | Not Started
3 | E5 | E5-T021 | Optimize assistant latency with snapshot caching | Cache snapshots and expensive computations to keep chat interactions responsive without using stale data for execution. | E1-T008, E1-T009 | BE | M | M | - Assistant responses use cached snapshots within a bounded TTL - Execution path always re-checks snapshot freshness before placing orders | backend/app/services/ai_trading_manager/context_cache.py | ai_assistant_enabled | Emit cache hit ratio and stale-cache blocks. | Not Started
3 | E5 | E5-T022 | Add tool permissions/scopes UI | Expose a UI to review which tools/scopes are enabled and to show when the system is in read-only vs execution-enabled mode. | E5-T007 | FE | M | M | - User can view current tool scopes and broker connection status - UI clearly indicates when execution is disabled | frontend/src/views/AssistantSettingsPage.tsx frontend/src/services/aiBroker.ts | ai_assistant_enabled | Track settings page views. | Not Started
3 | E5 | E5-T023 | Add accessibility and keyboard shortcuts | Ensure the always-present assistant panel is accessible and efficient with keyboard shortcuts. | E5-T006 | FE | M | L | - Panel supports focus management and ARIA labels - Shortcuts exist for open/close and jump-to-input | frontend/src/components/ai/AssistantPanel.tsx | ai_assistant_enabled | N/A (UX) | Not Started
3 | E5 | E5-T024 | Harden assistant UI error handling | Add robust error boundaries and broker-down/offline handling so the assistant degrades gracefully. | E1-T012 | FE | S | M | - UI shows a clear read-only state when broker is down - Errors are captured without breaking the main app navigation | frontend/src/components/ai/ErrorBoundary.tsx frontend/src/components/ai/BrokerStatusBanner.tsx | ai_assistant_enabled | Track UI error boundary captures. | Not Started
3 | E6 | E6-T013 | Add leader lock for scheduler (future-proof) | Add a leader lock abstraction so the scheduler can be made multi-process safe in the future, while remaining single-node today. | E6-T002 | DevOps | S | L | - Leader lock prevents multiple schedulers from running concurrently - Single-node behavior remains unchanged | backend/app/services/ai_trading_manager/monitoring/leader_lock.py | monitoring_enabled | Emit scheduler.leader_state changes. | Not Started
3 | E6 | E6-T014 | Integrate TradingView alerts as monitor triggers | Allow TradingView alerts to create monitor triggers/action cards (still execute-on-instruction/arming) to unify existing alert pipeline with AI TM. | E6-T003 | BE | M | M | - TradingView alerts can create monitor trigger events - No execution occurs without instruction/arming + RiskGate pass | backend/app/api/webhook.py backend/app/services/ai_trading_manager/monitoring/tv_alert_bridge.py | monitoring_enabled | Emit tv_alert→monitor trigger events and mapping errors. | Not Started
3 | E6 | E6-T015 | Define monitoring SLOs and alerting rules | Define SLOs for monitor job latency and failure rates and add alerting rules to detect degraded monitoring. | E6-T008 | DevOps | S | L | - SLO targets are documented and measurable - Alerts are emitted when failure/latency thresholds are exceeded | docs/ai_trading_manager/monitoring_slos.md backend/app/services/ai_trading_manager/anomaly_alerts.py | monitoring_enabled | Emit slo.breach events with current measurements. | Not Started

## Backend_Tasks
Phase | Epic ID | Task ID | Title | Description | Dependencies | Owner Type | Estimated Effort | Risk | Acceptance Criteria | Expected Files/Modules | Feature Flag(s) impacted | Telemetry/Audit | Status | Start Date | Due Date | Notes
0 | E0 | E0-T001 | Define AI Trading Manager data contracts | Create the canonical DTOs/schemas used across orchestrator, RiskGate, execution, reconciliation, and monitoring to enforce stable contracts and support replayable audits. |  | BE | M | M | - Schemas exist for BrokerSnapshot, LedgerSnapshot, TradeIntent, TradePlan, DecisionTrace, IdempotencyRecord, MonitorJob, ReconciliationDelta - All schemas are versioned (v1) and validated by unit tests | backend/app/schemas/ai_trading_manager.py backend/app/schemas/__init__.py | ai_assistant_enabled | Log schema_version + correlation_id in all AI TM endpoints; store schema_version on persisted records. | Not Started
0 | E0 | E0-T008 | Implement audit store query services | Create service-layer functions to write/read snapshots, traces, deltas, and exceptions with pagination and filters for UI consumption. | E0-T007 | BE | M | M | - Service functions support list-by-account and filter-by-time-window - All reads are bounded and paginated | backend/app/services/ai_trading_manager/audit_store.py backend/app/services/ai_trading_manager/__init__.py | ai_assistant_enabled | Trace audit_store query timings (p95) and row counts. | Not Started
0 | E0 | E0-T009 | Add correlation ID and decision ID plumbing | Ensure every AI TM request and internal action has correlation_id/decision_id for end-to-end traceability across logs, DB, and UI. | E0-T003 | BE | S | M | - FastAPI middleware attaches correlation_id to request context and response headers - DecisionTrace always includes correlation_id | backend/app/core/logging.py backend/app/services/ai_trading_manager/correlation.py | ai_assistant_enabled | Add correlation_id to all structured logs and error reports for AI TM routes. | Not Started
0 | E0 | E0-T010 | Add DecisionTrace query API endpoints | Expose read-only APIs to list and fetch DecisionTraces so the UI can show a decision timeline and allow debugging. | E0-T008, E0-T009 | BE | M | M | - GET /api/ai/decision-traces lists traces with filters (account_id, time, outcome) - GET /api/ai/decision-traces/{decision_id} returns full trace payload | backend/app/api/ai_trading_manager.py backend/app/api/routes.py | ai_assistant_enabled | Audit access to traces (who/when) and log query filter usage. | Not Started
0 | E0 | E0-T011 | Add Exceptions and reconciliation APIs | Expose APIs to list exceptions and reconciliation deltas; Phase 0 is read-only (no remediation actions executed). | E0-T008 | BE | M | M | - GET /api/ai/exceptions supports list + detail - GET /api/ai/reconciliation/deltas supports list + severity filtering | backend/app/api/ai_trading_manager.py | ai_assistant_enabled | Log exception read events and count by severity. | Not Started
0 | E0 | E0-T012 | Add retention and pruning job stub | Introduce a disabled-by-default retention job for snapshots/traces so data growth is controlled before enabling monitoring/execution. | E0-T008 | DevOps | S | L | - Retention settings exist (days) and default to no-op - Manual run prunes only AI TM tables and logs deletions | backend/app/services/ai_trading_manager/retention.py backend/app/core/config.py | monitoring_enabled | Emit retention.prune_run with deleted_row_counts per table. | Not Started
0 | E1 | E1-T001 | Define BrokerAdapter interface and DTOs | Introduce a multi-broker abstraction for snapshots, quotes, and order placement so AI TM can remain broker-agnostic while using Kite MCP first. | E0-T001 | BE | S | M | - BrokerAdapter interface exists with get_snapshot/get_quotes/place_order/get_orders/get_trades - DTOs cover Quote, OrderIntent, BrokerOrderAck and map to schemas | backend/app/services/ai_trading_manager/broker_adapter.py | kite_mcp_enabled | Log broker_adapter.selected with adapter name and account_id. | Not Started
0 | E1 | E1-T002 | Implement StubBrokerAdapter for local dev | Provide a predictable stub adapter so Phase 0 UI and pipelines can be built and tested without any broker connectivity. | E1-T001 | BE | S | L | - Stub adapter returns deterministic snapshots and quotes - Stub place_order returns a fake BrokerOrderAck and records intents for inspection | backend/app/services/ai_trading_manager/brokers/stub.py | kite_mcp_enabled | Log stub broker calls with request payload sizes. | Not Started
0 | E1 | E1-T003 | Wire BrokerAdapter selection via config and flags | Select the active broker adapter (stub vs kite_mcp) via feature flags and settings without affecting existing Zerodha KiteConnect flows. | E1-T002 | DevOps | S | M | - When kite_mcp_enabled=0, AI TM uses StubBrokerAdapter - Existing /api/zerodha endpoints remain unchanged | backend/app/core/config.py backend/app/services/ai_trading_manager/broker_factory.py | kite_mcp_enabled | Emit config.ai_tm.adapter metrics at startup. | Not Started
0 | E2 | E2-T001 | Define reconciliation delta schema and severity model | Define the delta model and severity classification to drive the Exceptions Center and remediation prioritization. | E0-T001 | BE | S | M | - ReconciliationDelta includes type, severity, broker_ref, expected_ref, and human summary - Severity rules are documented and unit tested | backend/app/schemas/ai_trading_manager.py backend/app/services/ai_trading_manager/reconciliation_rules.py | ai_assistant_enabled | Emit reconciliation.severity counts per run. | Not Started
0 | E2 | E2-T002 | Implement reconciler MVP (positions/orders) | Implement a first-pass reconciler that compares broker truth snapshots to ST expected ledger snapshots and emits bounded, actionable deltas. | E2-T001, E0-T002, E0-T006, E1-T002 | BE | M | H | - Given broker+ledger snapshots, reconciler produces deterministic deltas - Deltas cover missing fills, rejected orders, and stale positions | backend/app/services/ai_trading_manager/reconciler.py | ai_assistant_enabled | Log reconciliation.run with snapshot ids, delta_count, and severity histogram. | Not Started
0 | E2 | E2-T004 | Add on-demand reconciliation API | Expose an API to run reconciliation on-demand for a given account_id, returning deltas and opening exceptions as needed. | E2-T002, E0-T011 | BE | S | M | - POST /api/ai/reconcile runs reconciler and returns deltas - API is read-only with respect to broker (no broker writes) | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_reconcile_api.py | ai_assistant_enabled | Audit reconcile requests with user_id and delta_count. | Not Started
0 | E3 | E3-T001 | Define policy config format and storage | Define a policy config format (YAML/JSON) and store/load it so RiskGate evaluation is deterministic and auditable. | E0-T001 | BE | M | M | - Policy config schema exists with version and reason codes - Policy config can be loaded from file or DB and is logged in traces | backend/app/services/ai_trading_manager/policy_config.py backend/app/models/execution_policy.py | ai_execution_enabled | Audit policy config version used per evaluation. | Not Started
0 | E3 | E3-T002 | Implement deterministic RiskGate engine skeleton | Implement a pure-ish evaluator that takes (TradePlan, BrokerSnapshot, LedgerSnapshot) and returns allow/deny with reason codes. | E3-T001, E0-T001 | BE | M | H | - Same inputs produce same output (determinism test) - Outputs include allow/deny, reasons[], computed metrics | backend/app/services/ai_trading_manager/riskgate/engine.py | ai_execution_enabled | Emit riskgate.eval metrics (allow/deny counts) with policy_version. | Not Started
0 | E3 | E3-T003 | Implement core policy rules (risk limits) | Implement core policies: product constraints, max per-trade risk, daily loss cap, and max open positions. | E3-T002 | BE | M | H | - Violating policies produces deny with stable reason codes - Allow path computes risk metrics and includes them in the decision | backend/app/services/ai_trading_manager/riskgate/rules_core.py backend/tests/test_ai_tm_riskgate_core.py | ai_execution_enabled | Log riskgate.deny reason code distribution. | Not Started
0 | E3 | E3-T004 | Implement symbol and market-hours policy rules | Add allow/deny lists and market-hours/square-off rules (especially for MIS) using existing market hours utilities. | E3-T002 | BE | S | M | - Outside market hours, execution is denied with explicit reason - Symbol deny list blocks execution and proposes alternatives | backend/app/services/ai_trading_manager/riskgate/rules_market.py backend/app/core/market_hours.py | ai_execution_enabled | Audit market_hours denies including evaluated timestamp. | Not Started
0 | E3 | E3-T005 | Implement quote freshness and price sanity checks | Deny execution when quotes are stale or violate price band/liquidity sanity checks to avoid bad fills. | E1-T009, E3-T002 | BE | S | M | - Stale quotes produce deny with reason code QUOTE_STALE - Price sanity checks produce deny with reason code PRICE_SANITY_FAIL | backend/app/services/ai_trading_manager/riskgate/rules_quotes.py | ai_execution_enabled | Emit quote_stale_denies with quote_age_sec. | Not Started
0 | E4 | E4-T001 | Define OrderIntent and plan-to-order translation contract | Define the deterministic translation boundary from TradePlan to OrderIntent[] so execution remains reproducible. | E0-T001 | BE | S | M | - OrderIntent schema covers symbol, side, qty, order_type, product, limits - Translation contract is documented and unit tested | backend/app/schemas/ai_trading_manager.py backend/app/services/ai_trading_manager/execution/translator.py | ai_execution_enabled | Log translation outputs (counts) but not sensitive values. | Not Started
0 | E4 | E4-T002 | Implement IdempotencyStore service | Implement an IdempotencyStore on top of IdempotencyRecord to prevent duplicate executions across retries and UI resends. | E0-T004, E0-T008 | BE | M | H | - IdempotencyStore supports create-or-read semantics - Concurrent calls are safe (unique constraint enforced) | backend/app/services/ai_trading_manager/execution/idempotency_store.py | ai_execution_enabled | Emit idempotency.store collisions and resolution metrics. | Not Started
0 | E4 | E4-T003 | Implement ExecutionEngine dry-run skeleton | Implement a dry-run execution path that produces DecisionTrace outputs without placing broker orders. | E4-T001, E0-T003, E4-T002 | BE | M | M | - Dry-run returns translated OrderIntent[] and a DecisionTrace - No broker calls occur in dry-run mode | backend/app/services/ai_trading_manager/execution/engine.py backend/tests/test_ai_tm_execution_dry_run.py | ai_execution_enabled | Emit execution.dry_run metrics and plan_id. | Not Started
0 | E4 | E4-T004 | Add de-duplication guardrails for repeated submits | Ensure repeated UI submissions or duplicate webhook events cannot trigger duplicate executions by enforcing idempotency keys and request hashing. | E4-T002 | BE | S | H | - Same idempotency key returns the prior result without new broker orders - Different payload with same key is rejected and audited | backend/app/services/ai_trading_manager/execution/idempotency_store.py backend/app/api/ai_trading_manager.py | ai_execution_enabled | Audit idempotency_key reuse conflicts with payload hash. | Not Started
0 | E4 | E4-T005 | Implement execution kill switch and flag gating | Gate all broker write actions behind ai_execution_enabled and add a server-side kill switch for immediate rollback. | E1-T003 | DevOps | S | H | - When ai_execution_enabled=0, execution endpoints return a safe error and place zero orders - Kill switch state is logged and visible in UI | backend/app/core/config.py frontend/src/components/ai/ExecutionStatusBanner.tsx | ai_execution_enabled | Emit execution.kill_switch state changes and blocked execution attempts. | Not Started
0 | E5 | E5-T001 | Scaffold AI Orchestrator service and tool registry | Create the AI Orchestrator module structure and explicit tool registry so AI can reason while deterministic services decide. | E0-T001 | BE | M | M | - Orchestrator module exists with tool registry interfaces - A mock provider can run end-to-end without external LLM | backend/app/services/ai_trading_manager/orchestrator.py backend/app/services/ai_trading_manager/tools/__init__.py | ai_assistant_enabled | Audit tool invocations (tool_name, inputs_summary, duration) per decision. | Not Started
0 | E5 | E5-T002 | Add assistant messaging APIs (stub) | Add APIs to post a user message and fetch the assistant thread; Phase 0 returns stub responses and always creates a DecisionTrace. | E5-T001, E0-T010 | BE | M | M | - POST /api/ai/messages persists user message and returns assistant response - Each message creates a DecisionTrace even in stub mode | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_messages_api.py | ai_assistant_enabled | Emit ai_tm.message_received and ai_tm.response_sent events. | Not Started
0 | E6 | E6-T001 | Define MonitorJob schema and condition DSL | Define the MonitorJob and a minimal condition DSL to evaluate triggers deterministically and emit action cards. | E0-T001 | BE | M | M | - MonitorJob schema supports symbols, conditions, cadence, window - Condition DSL is versioned and validated | backend/app/schemas/ai_trading_manager.py backend/app/services/ai_trading_manager/monitoring/dsl.py | monitoring_enabled | Emit monitor.dsl.parse metrics and validation errors. | Not Started
0 | E6 | E6-T002 | Implement monitoring scheduler tick loop (disabled) | Implement a safe, bounded scheduler loop to evaluate monitor jobs; disabled by default to keep Phase 0 merge-safe. | E0-T005 | BE | M | M | - Scheduler can be started/stopped via monitoring_enabled - Work per cycle is capped to avoid long stalls | backend/app/services/ai_trading_manager/monitoring/scheduler.py | monitoring_enabled | Emit monitoring.scheduler cycle duration and job counts. | Not Started
0 | E6 | E6-T003 | Add MonitorJob CRUD APIs | Add APIs to create/update/delete/list MonitorJobs; Phase 0 stores jobs but evaluation can remain stubbed. | E6-T001, E0-T005 | BE | M | M | - CRUD endpoints exist and validate DSL - All operations create DecisionTrace entries | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_monitor_jobs_api.py | monitoring_enabled | Audit monitor job CRUD events with monitor_job_id. | Not Started
1 | E0 | E0-T014 | Add DecisionTrace export endpoint | Support exporting a DecisionTrace as JSON for debugging and offline review while scrubbing secrets. | E0-T010, E0-T017 | BE | S | M | - Export endpoint returns deterministic JSON for a given decision_id - Secrets/tokens are redacted in exported payload | backend/app/api/ai_trading_manager.py backend/app/services/ai_trading_manager/redaction.py | ai_assistant_enabled | Audit export events with user_id + decision_id. | Not Started
1 | E1 | E1-T005 | Implement Kite MCP client wrapper | Add a thin client wrapper to call Kite MCP endpoints with retries, timeouts, and structured error mapping for stable backend behavior. | E1-T001, E0-T009 | BE | M | H | - Client supports timeouts, retry with backoff, and rate limit handling - Errors are mapped to typed exceptions with safe user-facing messages | backend/app/services/ai_trading_manager/brokers/kite_mcp_client.py | kite_mcp_enabled | Emit kite_mcp.request metrics (latency, status, retries) and correlation_id. | Not Started
1 | E1 | E1-T007 | Add Kite MCP connect/status APIs | Expose backend APIs for initiating Kite MCP connection, checking status, and revoking tokens to support UI setup. | E1-T006 | BE | M | M | - Endpoints exist: GET status, POST connect/callback (as required), POST revoke - Status includes last_success_ts and scoped capabilities | backend/app/api/ai_broker_kite_mcp.py frontend/src/services/aiBroker.ts | kite_mcp_enabled | Emit kite_mcp.auth.status with connected=true/false and last_success_ts. | Not Started
1 | E1 | E1-T008 | Implement broker snapshot ingestion via Kite MCP | Fetch holdings/positions/orders/margins from Kite MCP and persist BrokerSnapshot for audit, reconciliation, and RiskGate inputs. | E1-T005, E0-T002 | BE | M | H | - get_snapshot returns BrokerSnapshot and persists it with snapshot_id - Snapshot ingestion is idempotent for identical as_of_ts | backend/app/services/ai_trading_manager/brokers/kite_mcp_adapter.py backend/app/services/ai_trading_manager/audit_store.py | kite_mcp_enabled | Log snapshot.fetch success/failure and snapshot freshness. | Not Started
1 | E1 | E1-T009 | Implement quotes fetch and cache via Kite MCP | Fetch quotes needed for monitoring and RiskGate checks, caching within a bounded TTL to control broker load. | E1-T005 | BE | M | M | - get_quotes returns Quote[] with as_of_ts - Quote age is exposed so RiskGate can deny stale quotes | backend/app/services/ai_trading_manager/brokers/kite_mcp_adapter.py backend/app/services/ai_trading_manager/quotes_cache.py | kite_mcp_enabled | Emit quotes.cache_hit/cache_miss and quote_age_sec distribution. | Not Started
1 | E1 | E1-T010 | Implement order placement via Kite MCP adapter | Place broker orders through Kite MCP with full correlation/idempotency context; broker remains the ultimate truth for order status. | E4-T008, E1-T005 | BE | M | H | - place_order sends OrderIntent and returns BrokerOrderAck with broker_order_id - Duplicate calls with same idempotency key do not create multiple broker orders | backend/app/services/ai_trading_manager/brokers/kite_mcp_adapter.py | ai_execution_enabled, kite_mcp_enabled | Audit order.place requests with correlation_id, idempotency_key, and broker_order_id. | Not Started
1 | E1 | E1-T011 | Implement orders/trades polling via Kite MCP | Support querying broker orders and trades for post-trade verification and reconciliation. | E1-T005 | BE | S | M | - get_orders/get_trades endpoints are wired and return normalized DTOs - Polling handles transient errors and respects rate limits | backend/app/services/ai_trading_manager/brokers/kite_mcp_adapter.py | kite_mcp_enabled | Emit broker.poll metrics (poll_count, latency, errors). | Not Started
1 | E1 | E1-T012 | Add broker-down degradation and circuit breaker | When Kite MCP is unavailable, degrade AI TM to read-only mode with explicit UI warnings and block execution. | E1-T005, E4-T005 | DevOps | M | H | - Circuit breaker opens on repeated failures and cools down automatically - Execution endpoints refuse to place orders when broker is down | backend/app/services/ai_trading_manager/brokers/circuit_breaker.py frontend/src/components/ai/BrokerStatusBanner.tsx | kite_mcp_enabled, ai_execution_enabled | Emit broker.circuit_state and broker.down incidents with duration. | Not Started
1 | E2 | E2-T006 | Schedule reconciliation after execution and on cadence | Run reconciler after each execution and on a safe cadence to ensure broker truth and expected ledger converge quickly. | E4-T009, E6-T002 | BE | M | H | - After successful execution, reconciliation runs automatically - Cadence run is bounded (max work per cycle) and can be disabled | backend/app/services/ai_trading_manager/reconciler_runner.py | monitoring_enabled | Emit reconciliation.runner metrics (runs, duration, failures). | Not Started
1 | E2 | E2-T007 | Implement post-trade verification polling | Poll broker order status until a terminal state or timeout, then reconcile; ensures partial fills and delayed completion are handled safely. | E1-T011, E4-T008 | BE | M | H | - Execution flow polls until COMPLETE/REJECTED/CANCELLED or timeout - Timeout produces an exception with actionable next steps | backend/app/services/ai_trading_manager/post_trade_verifier.py backend/tests/test_ai_tm_post_trade_verifier.py | ai_execution_enabled | Emit post_trade.verify metrics (polls, timeout_rate). | Not Started
1 | E2 | E2-T009 | Add exception action stubs (ack/snooze) | Implement non-trading exception actions (acknowledge/snooze) to manage noise while keeping remediation execution for Phase 2. | E0-T011 | BE | S | L | - POST /api/ai/exceptions/{id}/ack updates state and writes audit log - UI updates immediately and shows acknowledged state | backend/app/api/ai_trading_manager.py frontend/src/views/ExceptionsCenterPage.tsx | ai_assistant_enabled | Audit exception.ack events with user_id and reason (optional). | Not Started
1 | E3 | E3-T007 | Integrate RiskGate into plan→execute pipeline | Ensure every delegated execution runs RiskGate and is vetoed deterministically when any policy fails. | E3-T006, E5-T009, E4-T012 | BE | M | H | - Execution API refuses to place orders when RiskGate returns deny - DecisionTrace stores full RiskGate input references and result | backend/app/services/ai_trading_manager/orchestrator.py backend/app/services/ai_trading_manager/riskgate/engine.py | ai_execution_enabled | Emit riskgate.veto events with reason codes and decision_id. | Not Started
1 | E3 | E3-T009 | Add risk preview API (no execution) | Add an endpoint to evaluate RiskGate for a proposed TradePlan without placing orders, used by Plan Viewer and remediation flows. | E3-T007 | BE | S | M | - POST /api/ai/risk/preview returns RiskDecision for a plan - Preview creates a DecisionTrace marked as PREVIEW only | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_risk_preview.py | ai_execution_enabled | Emit risk.preview metrics and veto reason distribution. | Not Started
1 | E3 | E3-T010 | Compute and log risk metrics | Compute portfolio exposure metrics (concentration, leverage, open positions) and record them in RiskDecision for explainability. | E3-T007 | BE | M | M | - RiskDecision includes computed metrics - Metrics appear in DecisionTrace viewer | backend/app/services/ai_trading_manager/riskgate/metrics.py frontend/src/views/DecisionTracePage.tsx | ai_execution_enabled | Emit risk.metrics distributions (exposure, leverage) for monitoring. | Not Started
1 | E4 | E4-T007 | Implement plan-to-order translation for core order types | Translate TradePlan into broker-ready OrderIntent for common market/limit orders while preserving determinism. | E4-T001, E5-T009 | BE | M | M | - Translator supports BUY/SELL for MIS/CNC and market/limit skeleton - Unit tests cover translation edge cases and rounding | backend/app/services/ai_trading_manager/execution/translator.py backend/tests/test_ai_tm_translator.py | ai_execution_enabled | Log translation warnings (e.g., rounding adjustments). | Not Started
1 | E4 | E4-T008 | Implement broker order placement with idempotency | Place orders via BrokerAdapter only after RiskGate allow, using idempotency and correlation IDs to ensure safety. | E3-T007, E4-T002, E1-T010 | BE | L | H | - Given same idempotency_key, no more than one broker order is placed - DecisionTrace stores request/response for each broker order | backend/app/services/ai_trading_manager/execution/engine.py | ai_execution_enabled, kite_mcp_enabled | Emit execution.order_place metrics (success/failure, retries). | Not Started
1 | E4 | E4-T009 | Implement status polling and terminal state handling | Poll broker order status for placed orders and update DecisionTrace and expected ledger state without assuming immediate completion. | E1-T011, E4-T008 | BE | M | H | - Engine detects terminal states and records them - Non-terminal states result in bounded polling then exception | backend/app/services/ai_trading_manager/execution/status_poller.py | ai_execution_enabled | Emit execution.status_poll metrics and timeout count. | Not Started
1 | E4 | E4-T010 | Handle partial fills safely | Track partial fills and ensure no duplicate follow-up orders are placed; reconciliation must surface partial-fill exceptions when needed. | E4-T009, E2-T007 | BE | M | H | - Partial fills are detected and recorded in DecisionTrace - Reconciler emits partial-fill delta and exception when applicable | backend/app/services/ai_trading_manager/execution/fills.py backend/app/services/ai_trading_manager/reconciliation_rules.py | ai_execution_enabled | Emit execution.partial_fill events with filled_qty and remaining_qty. | Not Started
1 | E4 | E4-T012 | Implement execute API endpoint | Expose the backend execution endpoint that takes plan_id + idempotency_key + authorization message reference and returns an execution outcome. | E4-T003, E4-T008 | BE | M | H | - POST /api/ai/execute validates plan, runs RiskGate, and executes only on allow - Endpoint is gated by ai_execution_enabled and records DecisionTrace | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_execute_api.py | ai_execution_enabled | Audit execute attempts with outcome allow/deny/error and correlation_id. | Not Started
1 | E4 | E4-T014 | Add execution observability (metrics + structured logs) | Add metrics for retries, failures, veto rates, and broker latency to prioritize boring reliability. | E4-T012, E0-T009 | DevOps | S | M | - Metrics emitted for execute latency and error rate - Logs include correlation_id and idempotency_key | backend/app/services/ai_trading_manager/metrics.py backend/app/core/logging.py | monitoring_enabled | Emit execution metrics with labels: broker, outcome, retry_count. | Not Started
1 | E5 | E5-T007 | Implement tool router with explicit scopes | Implement tool routing in the orchestrator with explicit scope checks and auditing for ST tools and broker tools. | E5-T001, E1-T001 | BE | M | H | - Each tool call is logged with scope and parameters summary - Unauthorized tools are blocked and recorded in DecisionTrace | backend/app/services/ai_trading_manager/tool_router.py backend/app/services/ai_trading_manager/tools/*.py | ai_assistant_enabled | Emit tool_router.denied metrics and tool latency histograms. | Not Started
1 | E5 | E5-T008 | Implement intent parsing to TradeIntent | Parse user messages into a TradeIntent structure; combine LLM extraction with deterministic validation and fallback parsing. | E5-T002, E0-T001 | BE | M | H | - TradeIntent extraction validates symbols/side/product/constraints - Invalid intents return a clarifying question instead of executing | backend/app/services/ai_trading_manager/intent_parser.py backend/tests/test_ai_tm_intent_parser.py | ai_assistant_enabled | Emit intent.parse success/failure counts with reason categories. | Not Started
1 | E5 | E5-T009 | Implement deterministic PlanEngine normalization | Normalize and validate TradePlan/MonitorPlan structures deterministically so execution boundary is stable even if LLM output varies. | E5-T008, E0-T001 | BE | M | H | - PlanEngine rejects invalid plans with explicit errors - Normalized plans are stable (ordering, defaults, ids) for same input | backend/app/services/ai_trading_manager/plan_engine.py backend/tests/test_ai_tm_plan_engine.py | ai_assistant_enabled | Emit plan_engine.validation_error counts and plan_normalization timings. | Not Started
1 | E5 | E5-T013 | Implement message-as-authorization contract | Treat an explicit user message as authorization for delegated execution, without additional per-order confirmations, while still policy-gated. | E5-T002, E4-T012 | BE | M | H | - Execution requires authorization_message_id referencing the user message - DecisionTrace stores the exact user message used for authorization | backend/app/services/ai_trading_manager/orchestrator.py backend/app/schemas/ai_trading_manager.py | ai_execution_enabled | Audit authorization usage with message_id + decision_id. | Not Started
1 | E6 | E6-T004 | Implement deterministic condition evaluator | Evaluate monitor job conditions using quotes + portfolio state deterministically, producing triggers with reason details. | E1-T009, E6-T001 | BE | M | M | - Evaluator returns same result for same inputs - Evaluator records inputs_used in DecisionTrace | backend/app/services/ai_trading_manager/monitoring/evaluator.py backend/tests/test_ai_tm_monitor_evaluator.py | monitoring_enabled | Emit monitoring.eval metrics and trigger counts. | Not Started
1 | E6 | E6-T005 | Run monitor jobs on cadence and persist triggers | Run monitor jobs on schedule, persist trigger events, and push action cards to the assistant thread. | E6-T002, E6-T004, E0-T005 | BE | M | M | - Scheduler computes next_run_ts and persists last_run_ts - Triggers are persisted and deduped per (job, window) | backend/app/services/ai_trading_manager/monitoring/scheduler.py backend/app/services/ai_trading_manager/monitoring/store.py | monitoring_enabled | Emit monitoring.job_run metrics and trigger_dedupe hits. | Not Started
1 | E6 | E6-T007 | Integrate execute-on-instruction from triggers | When a trigger fires, assistant proposes a plan; execution occurs only when user explicitly instructs (message = authorization). | E6-T006, E4-T011 | BE | M | H | - Trigger flow creates a proposed plan and risk preview - No auto-execution occurs without explicit authorization message | backend/app/services/ai_trading_manager/orchestrator.py frontend/src/components/ai/cards/MonitorTriggerCard.tsx | monitoring_enabled, ai_execution_enabled | Audit trigger→plan proposals with monitor_job_id and decision_id. | Not Started
1 | E6 | E6-T008 | Add monitoring telemetry and failure handling | Add metrics and robust failure handling for the scheduler (per-job errors, retries, backoff) to avoid noisy loops. | E6-T005 | DevOps | S | M | - Scheduler logs failures per job and backs off - Metrics include job failure rate and mean run duration | backend/app/services/ai_trading_manager/monitoring/scheduler.py backend/app/services/ai_trading_manager/metrics.py | monitoring_enabled | Emit monitoring.scheduler.failure metrics and backoff state. | Not Started
2 | E0 | E0-T016 | Add playbook lifecycle audit events | Extend audit model to capture playbook creation, edits, arming/unarming, and runs with stable linking to DecisionTraces. | E5-T016 | BE | M | M | - Playbook actions create DecisionTrace entries with action_type=PLAYBOOK_* - UI can filter traces by playbook_id | backend/app/models/ai_trading_manager_traces.py backend/app/services/ai_trading_manager/audit_store.py | monitoring_enabled | Emit playbook.audit events with playbook_id + armed_state. | Not Started
2 | E0 | E0-T017 | Implement trace redaction and secret scrubbing | Prevent leakage of broker tokens, API keys, and PII into DecisionTrace storage and exports. | E1-T006, E0-T003 | BE | S | H | - All tokens/secrets are stored only in server-side secret tables - Trace payloads are scrubbed before persistence and export | backend/app/services/ai_trading_manager/redaction.py backend/tests/test_ai_tm_redaction.py | ai_assistant_enabled | Log redaction hits count and redact types (token/key/PII). | Not Started
2 | E1 | E1-T013 | Implement broker rate-limit budgeting | Coordinate broker API usage across monitoring, reconciliation, and execution using a shared budget to prevent throttling. | E6-T005, E1-T009 | BE | M | M | - Shared rate limiter enforces max requests/sec - Monitoring backs off automatically when budget is exhausted | backend/app/services/ai_trading_manager/brokers/rate_limit.py | monitoring_enabled, kite_mcp_enabled | Emit broker.rate_limit.throttles and per-component request counts. | Not Started
2 | E2 | E2-T010 | Implement remediation: resync expected ledger from broker truth | Add a safe remediation action to rebuild ST expected ledger state from broker truth snapshots, with full audit and guardrails. | E2-T006, E0-T002 | BE | M | H | - Resync is read-only w.r.t broker and only updates expected ledger - DecisionTrace records before/after snapshots and action outcome | backend/app/services/ai_trading_manager/remediation.py backend/app/api/ai_trading_manager.py | ai_assistant_enabled | Emit remediation.resync events with affected entity counts. | Not Started
2 | E2 | E2-T011 | Implement remediation: retry execution with safeguards | Allow retrying a failed execution via Exceptions Center using a new idempotency key, after re-running RiskGate and policy checks. | E4-T012, E3-T009 | BE | M | H | - Retry requires explicit user instruction (message = authorization) - RiskGate is re-evaluated and can veto the retry | backend/app/services/ai_trading_manager/remediation.py frontend/src/components/ai/ActionCards.tsx | ai_execution_enabled | Audit remediation.retry with original decision_id and new decision_id. | Not Started
2 | E2 | E2-T013 | Detect manual broker trades and expected-ledger drift | Classify deltas caused by manual broker actions and surface them as drift exceptions with clear remediation options. | E1-T008, E2-T002 | BE | M | M | - Reconciler labels drift vs ST-caused mismatches - Exceptions Center shows 'manual broker trade detected' with details | backend/app/services/ai_trading_manager/reconciliation_rules.py frontend/src/views/ExceptionsCenterPage.tsx | ai_assistant_enabled | Emit drift.detected events and counts per day. | Not Started
2 | E3 | E3-T012 | Add playbook-specific RiskGate rules | Add policies for armed playbooks: max frequency, allowed windows, and explicit arming requirement. | E6-T009, E3-T007 | BE | M | M | - Unarmed playbooks are denied with reason code PLAYBOOK_NOT_ARMED - Frequency limits deny when exceeded and produce deterministic reason | backend/app/services/ai_trading_manager/riskgate/rules_playbooks.py | monitoring_enabled | Emit playbook.riskgate denies with playbook_id. | Not Started
2 | E3 | E3-T013 | Add portfolio risk budgets and correlation constraints | Introduce portfolio-level risk budgets and correlation constraints; enforce as policy where feasible and record as advisory otherwise. | E5-T018, E3-T010 | BE | L | M | - RiskGate can deny when budgets are exceeded (configurable) - DecisionTrace stores budget inputs and computed correlation metrics | backend/app/services/ai_trading_manager/riskgate/rules_portfolio.py backend/app/services/risk_unified_store.py | ai_execution_enabled | Emit portfolio_budget metrics and deny rate. | Not Started
2 | E4 | E4-T015 | Implement safe sequencing for bracket/SL orders | Add deterministic sequencing for multi-leg executions (entry + stop-loss) with safe abort behavior. | E4-T008, E3-T003 | BE | L | H | - Multi-leg execution is idempotent per leg - If any leg fails, system stops and opens an exception | backend/app/services/ai_trading_manager/execution/sequencer.py | ai_execution_enabled | Emit execution.sequence events per leg with outcome. | Not Started
2 | E4 | E4-T017 | Support execution resume after interruptions | Allow resuming an interrupted execution from stored idempotency state without placing duplicate orders. | E4-T002, E4-T009 | BE | M | H | - Restarting the backend does not lose execution state - Resume continues polling and reconciliation safely | backend/app/services/ai_trading_manager/execution/engine.py backend/tests/test_ai_tm_execution_resume.py | ai_execution_enabled | Emit execution.resume events with prior broker_order_ids. | Not Started
2 | E5 | E5-T019 | Link playbook runs to traces and exceptions | Ensure playbook runs link to DecisionTrace and any resulting exceptions for review and debugging. | E0-T016, E2-T010 | BE | S | M | - Playbook run creates trace with playbook_id - Exceptions show originating playbook when applicable | backend/app/services/ai_trading_manager/orchestrator.py backend/app/models/ai_trading_manager_reconciliation.py | monitoring_enabled | Emit playbook.run.trace_linked events. | Not Started
2 | E6 | E6-T010 | Implement cautious automation runner | Execute only armed playbooks through the same RiskGate/ExecutionEngine pipeline, respecting kill switch and idempotency. | E6-T009, E4-T012 | BE | L | H | - Automation runs create DecisionTrace entries and are fully auditable - Kill switch disables automation immediately and stops new runs | backend/app/services/ai_trading_manager/automation/runner.py backend/tests/test_ai_tm_automation_runner.py | monitoring_enabled, ai_execution_enabled | Emit automation.run metrics and veto rates. | Not Started
2 | E6 | E6-T011 | Add monitor job backtesting/simulation mode | Allow simulating monitor jobs over historical quote data to validate conditions and reduce false triggers. | E6-T004 | BE | M | M | - Simulation produces deterministic trigger timelines - Simulation never places orders and is clearly labeled | backend/app/services/ai_trading_manager/monitoring/simulator.py frontend/src/views/MonitorJobSimPage.tsx | monitoring_enabled | Emit simulation.run metrics and duration. | Not Started
2 | E6 | E6-T012 | Add portfolio-level monitors and trigger cards | Add monitors for portfolio drawdown, drift, and concentration, emitting action cards and remediation suggestions. | E5-T018, E6-T005 | BE | L | M | - Portfolio monitors compute metrics deterministically - Trigger cards show metric deltas and as_of timestamps | backend/app/services/ai_trading_manager/monitoring/portfolio_monitors.py frontend/src/components/ai/cards/PortfolioMonitorCard.tsx | monitoring_enabled | Emit portfolio_monitor triggers and metric distributions. | Not Started
3 | E0 | E0-T018 | Add trace archival and configurable retention | Add configurable retention windows and optional archival/compression to keep audit data manageable while preserving required history. | E0-T012 | DevOps | M | M | - Retention window can be configured via env/DB settings - Archival job compresses older traces and keeps indexable metadata | backend/app/services/ai_trading_manager/retention.py backend/app/core/config.py | monitoring_enabled | Emit retention.archive_run metrics and failures. | Not Started
3 | E0 | E0-T019 | Add tamper-evident audit hashing | Add optional hash chaining across DecisionTraces to provide tamper evidence for the audit trail. | E0-T003 | BE | M | M | - Each DecisionTrace stores prev_hash and content_hash - Verifier detects any edited/deleted traces in a chain | backend/app/services/ai_trading_manager/audit_hashing.py backend/tests/test_ai_tm_audit_hashing.py | ai_assistant_enabled | Log audit_hash.verify results and mismatches. | Not Started
3 | E0 | E0-T020 | Publish audit coverage metrics | Expose metrics ensuring every AI action has a DecisionTrace and reconciliation record, enabling reliability-focused monitoring. | E0-T009, E2-T006 | DevOps | S | L | - Metrics expose counts for decisions without traces (should be 0) - Dashboard-ready metrics exist for veto rate, execution success rate, reconciliation OK rate | backend/app/api/system_events.py backend/app/services/ai_trading_manager/metrics.py | monitoring_enabled | Emit ai_tm.metrics snapshot on schedule and at startup. | Not Started
3 | E1 | E1-T015 | Add second broker adapter skeleton | Add a non-functional adapter skeleton (no execution) for a second broker to validate the abstraction and future roadmap. | E1-T001 | BE | S | L | - Adapter compiles and is selectable but returns NOT_IMPLEMENTED - Interface contract tests cover adapter behavior | backend/app/services/ai_trading_manager/brokers/angelone_mcp_adapter.py backend/tests/test_ai_tm_broker_adapter_contract.py | kite_mcp_enabled | Log adapter capability matrix at startup. | Not Started
3 | E1 | E1-T017 | Normalize broker instrument identifiers | Ensure reconciliation and quotes use a consistent symbol/instrument mapping across broker responses and ST internal keys. | E2-T002, E1-T008 | BE | M | M | - Mapping layer converts broker instrument ids to ST symbol keys - Reconciler uses mapped keys and reports mismatches clearly | backend/app/services/ai_trading_manager/symbol_mapping.py frontend/src/utils/symbolKey.ts | kite_mcp_enabled | Log symbol_mapping misses and unknown instrument ids. | Not Started
3 | E2 | E2-T014 | Optimize reconciliation with incremental diffs | Improve reconciler performance by diffing from prior runs and only evaluating changed broker/ledger entities. | E2-T006 | BE | M | M | - Reconciliation uses previous run cache when available - p95 reconciliation duration improves and is tracked | backend/app/services/ai_trading_manager/reconciler.py | monitoring_enabled | Emit reconciliation.duration p50/p95 and cache_hit ratio. | Not Started
3 | E2 | E2-T015 | Add anomaly alerts on reconciliation deltas | Detect spikes in exceptions/deltas and raise system events so operational issues are visible quickly. | E0-T020 | DevOps | S | M | - Alert triggers when exception rate exceeds threshold - Alerts link to Exceptions Center filters | backend/app/services/ai_trading_manager/anomaly_alerts.py frontend/src/services/systemEvents.ts | monitoring_enabled | Emit anomaly.alert events with thresholds and current rates. | Not Started
3 | E3 | E3-T017 | Unify reason codes with existing risk engine | Map AI TM RiskGate reason codes to existing risk engine reason taxonomy so UX and reporting are consistent. | E3-T003 | BE | M | M | - Common reason code mapping is documented and implemented - Frontend displays consistent copy across order flows | backend/app/services/managed_risk.py frontend/src/services/riskEngine.ts | ai_execution_enabled | Track reason code mapping misses. | Not Started
3 | E3 | E3-T018 | Add policy change safety checklist | Create a checklist and guardrails for policy changes (testing, rollout, monitoring) to reduce operational risk. | E3-T016 | DevOps | S | L | - Checklist exists and is referenced in Release_Checklists - Policy publish flow requires running preview tests | docs/ai_trading_manager/policy_change_checklist.md | monitoring_enabled | N/A (process) | Not Started
3 | E4 | E4-T018 | Add per-symbol/account concurrency locks | Prevent overlapping executions for the same symbol/account to reduce race conditions and reconciliation churn. | E4-T008 | BE | M | M | - Concurrent execute attempts for same symbol/account are serialized - Locks are bounded and released on failures/timeouts | backend/app/services/ai_trading_manager/execution/locks.py | ai_execution_enabled | Emit execution.lock contention metrics. | Not Started
3 | E5 | E5-T021 | Optimize assistant latency with snapshot caching | Cache snapshots and expensive computations to keep chat interactions responsive without using stale data for execution. | E1-T008, E1-T009 | BE | M | M | - Assistant responses use cached snapshots within a bounded TTL - Execution path always re-checks snapshot freshness before placing orders | backend/app/services/ai_trading_manager/context_cache.py | ai_assistant_enabled | Emit cache hit ratio and stale-cache blocks. | Not Started
3 | E6 | E6-T013 | Add leader lock for scheduler (future-proof) | Add a leader lock abstraction so the scheduler can be made multi-process safe in the future, while remaining single-node today. | E6-T002 | DevOps | S | L | - Leader lock prevents multiple schedulers from running concurrently - Single-node behavior remains unchanged | backend/app/services/ai_trading_manager/monitoring/leader_lock.py | monitoring_enabled | Emit scheduler.leader_state changes. | Not Started
3 | E6 | E6-T014 | Integrate TradingView alerts as monitor triggers | Allow TradingView alerts to create monitor triggers/action cards (still execute-on-instruction/arming) to unify existing alert pipeline with AI TM. | E6-T003 | BE | M | M | - TradingView alerts can create monitor trigger events - No execution occurs without instruction/arming + RiskGate pass | backend/app/api/webhook.py backend/app/services/ai_trading_manager/monitoring/tv_alert_bridge.py | monitoring_enabled | Emit tv_alert→monitor trigger events and mapping errors. | Not Started
3 | E6 | E6-T015 | Define monitoring SLOs and alerting rules | Define SLOs for monitor job latency and failure rates and add alerting rules to detect degraded monitoring. | E6-T008 | DevOps | S | L | - SLO targets are documented and measurable - Alerts are emitted when failure/latency thresholds are exceeded | docs/ai_trading_manager/monitoring_slos.md backend/app/services/ai_trading_manager/anomaly_alerts.py | monitoring_enabled | Emit slo.breach events with current measurements. | Not Started

## Frontend_Tasks
Phase | Epic ID | Task ID | Title | Description | Dependencies | Owner Type | Estimated Effort | Risk | Acceptance Criteria | Expected Files/Modules | Feature Flag(s) impacted | Telemetry/Audit | Status | Start Date | Due Date | Notes
0 | E2 | E2-T005 | Build read-only Exceptions Center UI | Create the Exceptions Center UI to list and inspect exceptions produced by the reconciler, without remediation actions in Phase 0. | E0-T011 | FE | M | M | - Exceptions Center lists exceptions with severity filters - Exception detail links to related DecisionTrace when available | frontend/src/views/ExceptionsCenterPage.tsx frontend/src/services/aiTradingManager.ts | ai_assistant_enabled | Log UI navigation events to exceptions center and exception_id viewed. | Not Started
0 | E5 | E5-T003 | Integrate assistant panel placeholder into MainLayout | Add the UI shell for a persistent right-side assistant panel, gated behind ai_assistant_enabled to keep Phase 0 merge-safe. |  | FE | M | M | - Assistant panel mounts in frontend/src/layouts/MainLayout.tsx - When flag off, layout and performance are unchanged | frontend/src/layouts/MainLayout.tsx frontend/src/components/ai/AssistantPanelShell.tsx | ai_assistant_enabled | Track assistant panel open/close state changes. | Not Started
0 | E5 | E5-T004 | Build basic chat UI and thread rendering | Implement basic chat UI components wired to the stub messaging APIs so the panel is end-to-end visible early. | E5-T002, E5-T003 | FE | M | M | - User can send a message and see a response in the panel - Messages are persisted/fetched via backend thread APIs | frontend/src/components/ai/AssistantPanel.tsx frontend/src/services/aiTradingManager.ts | ai_assistant_enabled | Emit UI analytics for messages sent and response latency. | Not Started
0 | E5 | E5-T005 | Scaffold DecisionTrace viewer route | Create a UI route and component skeleton to display DecisionTrace timelines fetched from backend trace APIs. | E0-T010 | FE | S | M | - DecisionTrace page loads trace by decision_id - UI handles missing/not-found traces gracefully | frontend/src/views/DecisionTracePage.tsx frontend/src/routes/AppRoutes.tsx | ai_assistant_enabled | Track trace page views with decision_id. | Not Started
1 | E2 | E2-T008 | Add exception detail view with trace linkage | Enhance Exceptions Center with a detail view that links to DecisionTrace and shows broker vs expected diffs. | E2-T005, E5-T012 | FE | M | M | - Exception detail shows delta breakdown and related broker ids - One-click navigation to DecisionTrace viewer works | frontend/src/views/ExceptionsCenterPage.tsx frontend/src/views/DecisionTracePage.tsx | ai_assistant_enabled | Track exception detail views and trace open actions. | Not Started
1 | E3 | E3-T008 | Render policy veto reason codes in UI | Show a clear veto card that maps deterministic reason codes to actionable explanations; no override is offered inside ST. | E3-T007, E5-T011 | FE | S | M | - UI shows deny reasons and suggested adjustments - UI does not provide any 'override' action for a veto | frontend/src/components/ai/VetoCard.tsx frontend/src/components/ai/reasonCodeCopy.ts | ai_execution_enabled | Track veto card impressions and reasons shown. | Not Started
1 | E5 | E5-T006 | Implement assistant panel always-present UX | Deliver the Phase 1 contract: assistant is always-present in the ST Web UI (persistent panel) with a clear collapsed state. | E5-T004 | FE | M | M | - Panel persists across routes and does not unmount on navigation - Collapsed state preserves unread indicators/action cards | frontend/src/layouts/MainLayout.tsx frontend/src/components/ai/AssistantPanel.tsx | ai_assistant_enabled | Track panel persistence bugs via UI error reporting. | Not Started
1 | E5 | E5-T010 | Build Plan Viewer UI | Render TradePlan details, normalized structure, and risk preview in a dedicated viewer and in action cards. | E5-T005, E3-T009 | FE | M | M | - Plan Viewer shows plan summary + raw JSON with copy/download - Risk preview results are displayed next to the plan | frontend/src/components/ai/PlanViewer.tsx frontend/src/services/aiTradingManager.ts | ai_assistant_enabled | Track plan viewer opens and risk preview latency. | Not Started
1 | E5 | E5-T011 | Implement Action Cards UI framework | Implement the Action Card framework (monitor, execute, veto, reconcile) so assistant can propose structured actions with trace links. | E5-T006 | FE | M | M | - Cards render consistently and support primary/secondary actions - Cards link to DecisionTrace and plan viewer | frontend/src/components/ai/ActionCards.tsx frontend/src/components/ai/cards/*.tsx | ai_assistant_enabled | Track card impressions and action clicks. | Not Started
1 | E5 | E5-T012 | Implement DecisionTrace viewer timeline | Implement a DecisionTrace timeline view: inputs → tools → RiskGate → orders → reconciliation, with filters and drilldowns. | E5-T005, E0-T010 | FE | M | M | - Timeline shows tool calls and risk decisions in order - Viewer links broker_order_ids to exception details when present | frontend/src/views/DecisionTracePage.tsx frontend/src/components/ai/TraceTimeline.tsx | ai_assistant_enabled | Track trace viewer load time and error rates. | Not Started
1 | E5 | E5-T014 | Add assistant navigation to Exceptions Center | Add assistant shortcuts to open Exceptions Center and filtered views tied to current decisions. | E2-T005, E5-T011 | FE | S | L | - Action card can open Exceptions Center with prefilled filters - Exceptions Center can navigate back to related trace | frontend/src/components/ai/ActionCards.tsx frontend/src/routes/AppRoutes.tsx | ai_assistant_enabled | Track navigation from assistant to exceptions center. | Not Started
1 | E5 | E5-T015 | Add frontend feature flags for AI TM | Implement ai_assistant_enabled/ai_execution_enabled/kite_mcp_enabled/monitoring_enabled UI gating via query params and local storage. |  | FE | S | L | - Flags can be toggled via URL params for dev - UI hides AI TM features when flags are off | frontend/src/config/aiFeatures.ts frontend/src/App.tsx | ai_assistant_enabled, ai_execution_enabled, kite_mcp_enabled, monitoring_enabled | Track feature flag states in client-side diagnostics logs. | Not Started
1 | E6 | E6-T006 | Render trigger action cards in assistant UI | Display monitoring triggers as assistant action cards with quick actions (view details, propose plan, acknowledge). | E5-T011, E6-T005 | FE | M | M | - Trigger cards appear in assistant panel with timestamps - Cards link to monitor job and decision trace | frontend/src/components/ai/cards/MonitorTriggerCard.tsx | monitoring_enabled | Track trigger card impressions and acknowledgements. | Not Started
2 | E2 | E2-T012 | Add remediation suggestions (close/hedge proposals) | Generate deterministic remediation suggestions for risky exceptions (e.g., approaching MIS square-off) as action cards; execution still requires instruction/arming. | E6-T012, E3-T004 | FE | M | M | - UI shows remediation suggestion cards with clear rationale - No broker orders are placed unless user instructs and policy allows | frontend/src/components/ai/RemediationCards.tsx backend/app/services/ai_trading_manager/remediation_suggestions.py | ai_assistant_enabled | Track suggestion impressions and user follow-through. | Not Started
2 | E5 | E5-T016 | Build playbook library UI | Implement UI to save, edit, and run playbooks (saved intents/plans) as reusable workflows. | E5-T010 | FE | L | M | - User can save a plan as a playbook and list playbooks - Running a playbook creates a DecisionTrace and action cards | frontend/src/views/PlaybooksPage.tsx frontend/src/services/aiTradingManager.ts | monitoring_enabled | Track playbook create/edit/run events. | Not Started
2 | E5 | E5-T017 | Implement arming UX for playbooks | Implement explicit arming/unarming flow for automations with clear safety messaging and kill switch visibility. | E6-T009, E5-T016 | FE | M | H | - Arming requires explicit user action and is clearly indicated - UI shows when kill switch disables automation | frontend/src/components/ai/PlaybookArmingDialog.tsx | monitoring_enabled | Audit arming toggles (playbook_id, user_id) via backend. | Not Started
2 | E5 | E5-T018 | Add portfolio decision intelligence views | Add views for drift, correlation, and risk budgets that inform suggestions while keeping execution deterministic and policy-gated. | E3-T010 | FE | L | M | - Dashboard cards show drift/correlation summaries - Data sources and as_of timestamps are shown for transparency | frontend/src/views/PortfolioDIPanel.tsx frontend/src/services/analytics.ts | ai_assistant_enabled | Track DI view usage and load times. | Not Started
3 | E3 | E3-T016 | Build policy editor UI (admin-only) | Provide an admin-only UI for editing policy configs safely, with validation and preview. | E3-T014, E3-T009 | FE | L | M | - Editor validates schema and shows preview results - Changes are versioned and require explicit publish step | frontend/src/views/PolicyEditorPage.tsx frontend/src/services/aiTradingManager.ts | ai_execution_enabled | Audit policy edit/publish events with user_id. | Not Started
3 | E4 | E4-T020 | Generate audit-grade execution report | Generate a human-readable execution report (inputs, policies, orders, outcomes) derived from DecisionTrace for post-mortem and review. | E0-T013 | FE | M | L | - Report view renders from DecisionTrace deterministically - Report includes riskgate result, broker order ids, reconciliation outcome | frontend/src/views/DecisionTracePage.tsx frontend/src/components/ai/ExecutionReport.tsx | ai_assistant_enabled | Track report views and export actions. | Not Started
3 | E5 | E5-T020 | Add regime and volatility overlay cards | Add advisory-only regime/volatility overlays to inform decisions while keeping execution boundary deterministic and policy-gated. | E5-T018 | FE | M | L | - Overlay cards clearly marked as advisory - No automated execution is triggered by overlays | frontend/src/components/ai/RegimeOverlayCard.tsx | ai_assistant_enabled | Track overlay card impressions. | Not Started
3 | E5 | E5-T022 | Add tool permissions/scopes UI | Expose a UI to review which tools/scopes are enabled and to show when the system is in read-only vs execution-enabled mode. | E5-T007 | FE | M | M | - User can view current tool scopes and broker connection status - UI clearly indicates when execution is disabled | frontend/src/views/AssistantSettingsPage.tsx frontend/src/services/aiBroker.ts | ai_assistant_enabled | Track settings page views. | Not Started
3 | E5 | E5-T023 | Add accessibility and keyboard shortcuts | Ensure the always-present assistant panel is accessible and efficient with keyboard shortcuts. | E5-T006 | FE | M | L | - Panel supports focus management and ARIA labels - Shortcuts exist for open/close and jump-to-input | frontend/src/components/ai/AssistantPanel.tsx | ai_assistant_enabled | N/A (UX) | Not Started
3 | E5 | E5-T024 | Harden assistant UI error handling | Add robust error boundaries and broker-down/offline handling so the assistant degrades gracefully. | E1-T012 | FE | S | M | - UI shows a clear read-only state when broker is down - Errors are captured without breaking the main app navigation | frontend/src/components/ai/ErrorBoundary.tsx frontend/src/components/ai/BrokerStatusBanner.tsx | ai_assistant_enabled | Track UI error boundary captures. | Not Started

## Data_DB_Tasks
Phase | Epic ID | Task ID | Title | Description | Dependencies | Owner Type | Estimated Effort | Risk | Acceptance Criteria | Expected Files/Modules | Feature Flag(s) impacted | Telemetry/Audit | Status | Start Date | Due Date | Notes
0 | E0 | E0-T002 | Add snapshot persistence models | Persist BrokerSnapshot and LedgerSnapshot as immutable snapshots to support deterministic RiskGate inputs, reconciliation, and audit replay. | E0-T001 | DB | M | M | - SQLAlchemy models for broker_snapshots and ledger_snapshots exist - Snapshots are append-only and keyed by (account_id, as_of_ts, source) | backend/app/models/ai_trading_manager_snapshots.py backend/app/models/__init__.py | kite_mcp_enabled | Audit snapshot_ingest events with snapshot_id, account_id, as_of_ts, source. | Not Started
0 | E0 | E0-T003 | Add DecisionTrace persistence models | Persist DecisionTrace as the always-on audit artifact for every AI decision and delegated action, including tool calls and outcomes. | E0-T001 | DB | M | H | - DecisionTrace tables store user_message, inputs_used snapshot references, tool calls, riskgate result, and final outcome - Every persisted trace has a stable decision_id and correlation_id | backend/app/models/ai_trading_manager_traces.py backend/app/models/__init__.py | ai_assistant_enabled | All writes emit structured log ai_tm.decision_trace.persisted with decision_id + correlation_id. | Not Started
0 | E0 | E0-T004 | Add IdempotencyRecord persistence model | Persist idempotency keys and resulting broker order IDs to guarantee at-most-once order placement across retries, refreshes, and UI resends. | E0-T001 | DB | S | H | - IdempotencyRecord table enforces unique key per scope (account_id + key) - Record stores status + broker_order_ids + first_seen_ts | backend/app/models/ai_trading_manager_idempotency.py backend/app/models/__init__.py | ai_execution_enabled | Log idempotency_hit/idempotency_miss and record latency for ExecutionEngine calls. | Not Started
0 | E0 | E0-T005 | Add MonitorJob persistence models | Persist MonitorJob definitions and trigger history to support monitoring-as-a-service and action cards. | E0-T001 | DB | M | M | - MonitorJob table stores symbols, conditions, cadence, window, enabled state - Trigger events are persisted with references back to MonitorJob and snapshots | backend/app/models/ai_trading_manager_monitoring.py backend/app/models/__init__.py | monitoring_enabled | Emit monitoring.job_created/job_triggered events with monitor_job_id + correlation_id. | Not Started
0 | E0 | E0-T006 | Add reconciliation delta and exception models | Persist ReconciliationDelta and Exceptions as first-class operational artifacts for the Exceptions Center and remediation flows. | E0-T001 | DB | M | M | - ReconciliationDelta and Exception tables store severity, classification, and references to broker/ledger snapshots - Exceptions can be acknowledged and tracked over time | backend/app/models/ai_trading_manager_reconciliation.py backend/app/models/__init__.py | ai_assistant_enabled | Emit reconciliation.delta_created and exception.opened/acknowledged events. | Not Started
0 | E0 | E0-T007 | Create Alembic migration for AI Trading Manager tables | Add a single Phase 0 migration that introduces the AI Trading Manager tables without impacting existing order flows. | E0-T002, E0-T003, E0-T004, E0-T005, E0-T006 | DB | S | M | - alembic upgrade head creates new tables successfully on SQLite - Existing migrations and tests continue to pass | backend/alembic/versions/xxxx_ai_trading_manager_foundation.py | ai_assistant_enabled | Log migration version + db schema version at app startup. | Not Started
0 | E2 | E2-T003 | Persist reconciliation runs and open exceptions | Persist reconciliation outcomes and open exceptions for medium/high severity deltas so operations can be managed in the UI. | E2-T002, E0-T006, E0-T008 | DB | M | M | - Reconciliation runs are stored with references to snapshot ids - Exceptions open automatically for severity>=M and dedupe by (type, broker_ref) | backend/app/services/ai_trading_manager/audit_store.py backend/app/models/ai_trading_manager_reconciliation.py | ai_assistant_enabled | Emit exception.opened with exception_id + severity. | Not Started
1 | E0 | E0-T013 | Expand DecisionTrace fields for execution and reconciliation | Extend DecisionTrace to store RiskGate results, broker acks, status polls, and reconciliation outcomes for audit-grade replay. | E0-T003, E4-T008, E2-T006 | DB | M | M | - DecisionTrace schema includes riskgate_result, orders_submitted, reconciliation_result - Trace viewer shows these fields end-to-end | backend/app/models/ai_trading_manager_traces.py backend/alembic/versions/xxxx_ai_tm_trace विस्तार.py | ai_execution_enabled | Log decision_trace schema upgrades and migration timing. | Not Started
1 | E1 | E1-T006 | Implement server-side Kite MCP token storage | Store Kite MCP tokens server-side only using the existing encryption utilities; frontend never receives broker credentials. | E1-T005 | DB | M | H | - Tokens are encrypted at rest (reuse backend/app/core/crypto.py) - No token fields are returned by any API responses | backend/app/models/broker.py backend/app/services/ai_trading_manager/brokers/kite_mcp_tokens.py | kite_mcp_enabled | Audit token create/refresh/revoke events without logging the token value. | Not Started
2 | E1 | E1-T014 | Add multi-account broker partitioning | Support account_id scoping across snapshots, idempotency, and monitor jobs to prepare for multi-account use. | E0-T007 | DB | M | M | - All AI TM tables are partitioned by account_id - APIs require account_id and enforce isolation | backend/app/models/ai_trading_manager_*.py backend/app/api/ai_trading_manager.py | ai_assistant_enabled | Log account_id on all AI TM actions and enforce access checks. | Not Started
2 | E3 | E3-T014 | Add policy versioning and pin evaluations to version | Version policies and record which version was used for each decision so replay is accurate over time. | E3-T001, E0-T003 | DB | M | M | - Policy versions are immutable and selectable - DecisionTrace stores policy_version and config hash | backend/app/models/execution_policy.py backend/app/services/ai_trading_manager/policy_config.py | ai_execution_enabled | Audit policy.version_used per decision. | Not Started
2 | E4 | E4-T016 | Implement expected ledger update saga | Update ST expected ledger as a durable saga around execution steps, then reconcile against broker truth to converge. | E2-T006, E0-T002 | DB | L | H | - Expected ledger updates are transactional and replayable - Reconciler detects divergence and opens exceptions | backend/app/services/ai_trading_manager/ledger.py backend/app/models/ai_trading_manager_snapshots.py | ai_execution_enabled | Emit ledger.expected_update events with entity counts. | Not Started
2 | E6 | E6-T009 | Implement playbook arming model (backend) | Persist arming state and enforce explicit enablement before any automation can execute. | E5-T016, E3-T012 | DB | M | H | - Playbook armed_state is persisted and audited - Automation runner refuses to execute unarmed playbooks | backend/app/models/ai_trading_manager_playbooks.py backend/alembic/versions/xxxx_ai_tm_playbooks.py | monitoring_enabled | Audit playbook.armed_state changes with user_id. | Not Started

## QA_Testing
Phase | Epic ID | Task ID | Title | Description | Dependencies | Owner Type | Estimated Effort | Risk | Acceptance Criteria | Expected Files/Modules | Feature Flag(s) impacted | Telemetry/Audit | Status | Start Date | Due Date | Notes
0 | E1 | E1-T004 | Build broker-mock harness for integration tests | Create a deterministic in-process broker mock to simulate fills, rejects, and delayed status updates for integration tests and CI. | E1-T001 | QA | M | M | - Mock supports scenarios: success, reject, partial fill, delayed completion - Integration tests can run without external broker connectivity | backend/tests/helpers/broker_mock.py backend/tests/test_ai_tm_broker_mock.py | kite_mcp_enabled | Log broker_mock scenario selection per test. | Not Started
0 | E3 | E3-T006 | Add RiskGate determinism and rule unit tests | Add unit tests proving determinism and correctness of individual rules to protect the execution boundary. | E3-T003, E3-T004, E3-T005 | QA | M | M | - Determinism test: same inputs -> same output across multiple runs - Rule tests cover allow and deny cases for each rule | backend/tests/test_ai_tm_riskgate_determinism.py backend/tests/test_ai_tm_riskgate_rules.py | ai_execution_enabled | N/A (tests) | Not Started
0 | E4 | E4-T006 | Add idempotency and dedupe integration tests | Add tests proving at-most-once behavior across retries and concurrent requests using the stub broker adapter. | E4-T004, E1-T004 | QA | M | M | - Concurrent execute calls with same key place at most one mock broker order - DecisionTrace shows stable correlation IDs across retries | backend/tests/test_ai_tm_idempotency.py | ai_execution_enabled | N/A (tests) | Not Started
1 | E0 | E0-T015 | Add RiskGate replay harness (dry-run) | Enable re-evaluating RiskGate from stored snapshots and plans to validate determinism and diagnose veto/allow decisions. | E3-T007, E0-T010 | QA | M | M | - Replay endpoint returns identical allow/deny result for the same stored inputs - Replay is read-only and never places broker orders | backend/app/api/ai_trading_manager.py backend/tests/test_ai_tm_riskgate_replay.py | ai_assistant_enabled | Log replay runs with input snapshot ids + outcome. | Not Started
1 | E3 | E3-T011 | Enforce no-override policy for AI execution | Ensure there is no internal override path for AI delegated execution; policy veto is mandatory and cannot be bypassed within ST. | E3-T007 | QA | S | H | - Attempting to call execution endpoints without RiskGate allow returns 403/deny - Frontend does not render any override controls for vetoed trades | backend/tests/test_ai_tm_no_override.py frontend/src/components/ai/VetoCard.tsx | ai_execution_enabled | N/A (tests) | Not Started
1 | E4 | E4-T011 | Enforce execute-on-instruction semantics | Ensure trades are executed only when the user message is an explicit instruction; monitoring triggers and suggestions never auto-execute in Phase 1. | E5-T013 | QA | S | H | - Suggested plans do not execute without a user instruction message - Execution endpoints require an authorization_message_id | backend/tests/test_ai_tm_execute_on_instruction.py backend/app/services/ai_trading_manager/orchestrator.py | ai_execution_enabled | N/A (tests) | Not Started
1 | E4 | E4-T013 | Add broker integration tests for execution scenarios | Add integration tests using broker-mock harness for rejected orders, delayed completion, and partial fills. | E4-T012, E1-T004 | QA | M | M | - Tests cover reject, delayed status, partial fill scenarios - No test places real broker orders | backend/tests/test_ai_tm_execution_integration.py | ai_execution_enabled | N/A (tests) | Not Started
3 | E1 | E1-T016 | Add broker capability discovery and contract tests | Add adapter capability discovery and contract tests to detect breaking changes in MCP endpoints early. | E1-T005 | QA | M | M | - Contract tests validate required fields and error mapping - CI can run against broker-mock and optionally against real MCP in staging | backend/tests/test_ai_tm_kite_mcp_contract.py | kite_mcp_enabled | Emit contract_test results as system events. | Not Started
3 | E2 | E2-T016 | Document ledger rebuild runbook | Write an operator runbook for rebuilding expected ledger from broker truth, including rollback strategy and audit requirements. | E2-T010 | QA | S | L | - Runbook exists with step-by-step commands and verification steps - Rollback plan is included | docs/ai_trading_manager/runbooks/ledger_rebuild.md | monitoring_enabled | N/A (documentation) | Not Started
3 | E3 | E3-T015 | Add policy snapshot tests | Add snapshot tests for representative policies to detect unintended changes in rule behavior. | E3-T014 | QA | M | L | - Snapshot tests cover common allow/deny scenarios - CI fails on unexpected policy behavior changes | backend/tests/test_ai_tm_policy_snapshots.py | ai_execution_enabled | N/A (tests) | Not Started
3 | E4 | E4-T019 | Add chaos tests for broker timeouts | Add chaos-style tests simulating broker timeouts and flaky responses to validate idempotency and recovery behavior. | E1-T004, E4-T017 | QA | M | M | - Chaos tests demonstrate no duplicate orders - Exceptions are opened with actionable remediation | backend/tests/test_ai_tm_execution_chaos.py | ai_execution_enabled | N/A (tests) | Not Started

## Release_Checklists
Phase | Checklist Item | Owner Type | Done? | Notes
0 | Confirm all Phase 0 routes are behind ai_assistant_enabled and do not affect existing /api/orders flows | QA
0 | Verify ai_execution_enabled defaults to OFF and broker write paths are unreachable | QA
0 | Run alembic upgrade head on fresh SQLite DB and verify new tables only | DB
0 | Smoke test Exceptions Center read-only UI with stub data | QA
0 | Rollback plan: disable ai_assistant_enabled + monitoring_enabled | DevOps
1 | Verify assistant panel is always-present across routes | QA
1 | Verify 'message = authorization' requires explicit instruction + stores authorization_message_id | QA
1 | Verify RiskGate veto places zero broker orders and creates DecisionTrace | QA
1 | Verify idempotency: repeated execute call does not place duplicate orders | QA
1 | Verify broker truth reconciliation runs after trade and Exceptions Center stays clean for a typical day | QA
1 | Safe rollout: enable kite_mcp_enabled first (read-only), then ai_execution_enabled for allowlisted account | DevOps
1 | Rollback plan: flip ai_execution_enabled OFF (kill switch) then kite_mcp_enabled OFF | DevOps
2 | Verify automation requires explicit arming and kill switch disables new automation runs | QA
2 | Verify playbook runs are fully traced and reconcilable | QA
2 | Safe rollout: staged arming (single playbook, limited symbols), monitor veto/exception rates | DevOps
3 | Verify audit retention/archival jobs and tamper-evidence verifier | QA
3 | Verify anomaly alerts/SLOs fire appropriately in staging | DevOps

## Risks_Dependencies
Top Risks
Risk | Impact | Likelihood | Mitigation | Related Tasks
Kite MCP downtime / high latency | Execution/monitoring may stall; stale snapshots; user confusion | H | Circuit breaker + degrade to read-only; bounded retries; explicit UI status | E1-T012, E2-T006, E5-T024
Duplicate orders due to retries/races | Financial loss; loss of trust | H | IdempotencyStore + unique constraints; payload-hash guardrails; chaos tests | E0-T004, E4-T002, E4-T004, E4-T019
RiskGate non-determinism or policy gaps | Unsafe executions; hard-to-debug behavior | M | Pure-ish engine, determinism tests, policy versioning, snapshot tests | E3-T002, E3-T006, E3-T014, E3-T015
Expected ledger diverges from broker truth | Exceptions noise; wrong UI state; unsafe follow-up actions | M | Broker snapshots as truth; post-trade verify; reconciliation cadence; drift classification | E1-T008, E2-T007, E2-T013, E4-T016
Secrets leak into traces/logs | Security incident; account compromise | M | Server-side token storage; redaction; export scrubber | E1-T006, E0-T017, E0-T014
Automation executes without explicit user intent | Unexpected trades; high severity incident | L | Arming model + execute-on-instruction; kill switch; tests | E6-T009, E6-T010, E4-T011
Critical Path (Sequencing)
Milestone | Depends On (Tasks) | Notes
Phase 0 foundation usable | E0-T007, E0-T010, E1-T002, E2-T004, E5-T004 | Audit store + stub broker + read-only exceptions + assistant shell are live behind flags.
Broker truth snapshots via Kite MCP | E1-T005, E1-T006, E1-T008 | Snapshot ingestion must precede reliable reconciliation and execution.
Deterministic veto boundary | E3-T006, E3-T007, E3-T008 | Never allow execution without RiskGate allow; veto UI must be clear.
Idempotent execution to broker | E4-T002, E4-T008, E4-T012 | Idempotency must exist before live order placement.
Always-on audit and trace viewer | E0-T003, E0-T010, E5-T012 | DecisionTrace must be available before enabling delegated execution for real use.
Reconciliation confidence | E2-T006, E2-T007, E2-T008 | Post-trade verification + reconciliation must keep exceptions bounded.