## Sheet1
sprint#	group#	group task description.	task#	task description	deviations (from original plan)	status	remarks	pending work
S01	G01	Backend scaffolding and FastAPI project setup	S01_G01_TB001	Initialize backend repository with FastAPI project structure (src/app, tests, config folders).	Used backend/app instead of src/app to keep backend isolated.	implemented	Backend skeleton (app, core, api, tests folders) created.
S01	G01	Backend scaffolding and FastAPI project setup	S01_G01_TB002	Set up base FastAPI application with root and /health endpoints.	Also added pytest-based tests for / and /health as part of this task.	implemented	FastAPI app with root and /health endpoints implemented and tested.
S01	G01	Backend scaffolding and FastAPI project setup	S01_G01_TB003	Configure environment-based settings (dev/prod) using pydantic settings or similar.	Using pydantic BaseSettings with ST_ env prefix and .env support.	implemented	Environment-aware settings wired into app and health responses.
S01	G02	Frontend scaffolding and React/TypeScript/Material UI setup	S01_G02_TF001	Create React TypeScript app with Material UI and routing (React Router).	Used Vite react-ts template with a dark MUI theme.	implemented	React+TS app scaffolded with basic app shell.
S01	G02	Frontend scaffolding and React/TypeScript/Material UI setup	S01_G02_TF002	Implement base layout with top bar and sidebar navigation placeholders.	Implemented a drawer-based layout with MUI AppBar and sidebar.	implemented	Top bar + side nav with placeholder pages (Dashboard, Queue, Orders, Analytics, Settings).
S01	G02	Frontend scaffolding and React/TypeScript/Material UI setup	S01_G02_TF003	Wire basic API call from frontend to backend /health endpoint and display connection status.	Health check uses a simple fetch hook against /health and shows status in a Chip.	implemented	API status indicator wired to backend /health endpoint.
S01	G03	Tooling, Git workflow, and initial documentation	S01_G03_TB001	Configure linting/formatting (black/isort/ruff) and pre-commit hooks for backend.	Configured Black, isort, Ruff, and pre-commit in backend with a shared pyproject.	implemented	Backend codebase can be auto-formatted and linted; hooks available via pre-commit.
S01	G03	Tooling, Git workflow, and initial documentation	S01_G03_TF002	Configure linting/formatting (ESLint/Prettier) for frontend.	Used Vite flat ESLint config with eslint-config-prettier and a simple Prettier setup.	implemented	Frontend has ESLint + Prettier with npm scripts for linting and formatting.
S01	G03	Tooling, Git workflow, and initial documentation	S01_G03_TB003	Create initial README with project overview and setup steps.	Expanded existing README instead of creating a separate doc.	implemented	README now documents backend/frontend run, test, and lint/format commands.
S02	G01	Design core SQLite schema for alerts, orders, strategies, risk settings	S02_G01_TB001	Design database schema for alerts, orders, strategies, risk_settings, positions, analytics_trades tables.	Captured schema as a Markdown document with SQLite-focused CREATE TABLE statements and indexes instead of direct migrations.	implemented	Core tables (strategies, risk_settings, alerts, orders, positions, analytics_trades) are designed with keys, checks, and indexes.
S02	G01	Design core SQLite schema for alerts, orders, strategies, risk settings	S02_G01_TB002	Review schema for extensibility and alignment with PRD (manual queue, risk, analytics).	Included explicit notes on AUTO/MANUAL modes, manual queue, risk engine, and analytics alignment inside the schema doc.	implemented	Schema reviewed for extensibility and alignment with PRD, including risk scopes and simulation support.
S02	G02	Implement ORM models and migrations	S02_G02_TB001	Implement SQLAlchemy ORM models for core tables (alerts, orders, strategies, risk_settings).	Used SQLAlchemy 2.0 typed ORM models grouped under app.models.trading.	implemented	Core tables (strategies, risk_settings, alerts, orders, positions, analytics_trades) are mapped as ORM entities.
S02	G02	Implement ORM models and migrations	S02_G02_TB002	Set up Alembic (or equivalent migration tool) for managing schema migrations.	Initialized Alembic in backend/ with env.py wired to Settings and an initial migration creating the core tables.	implemented	Alembic upgrade head creates the SQLite schema from ORM metadata.
S02	G02	Implement ORM models and migrations	S02_G02_TB003	Implement DB session management and dependency injection in FastAPI.	Configured a synchronous SessionLocal and get_db FastAPI dependency; tests use the same engine.	implemented	DB session management is in app.db.session, and README documents Alembic + testing commands.
S02	G03	Backend admin APIs for strategies and risk settings	S02_G03_TB001	Create CRUD APIs to manage strategies (list/create/update).	Exposed REST APIs under /api/strategies for list/create/update operations.	implemented	Strategies can be created and updated via FastAPI endpoints with tests covering basic flows.
S02	G03	Backend admin APIs for strategies and risk settings	S02_G03_TB002	Create CRUD APIs to manage global and per-strategy risk_settings.	Exposed REST APIs under /api/risk-settings with filters for scope and strategy.	implemented	Global and per-strategy risk_settings can be created and queried; uniqueness and scope rules enforced.
S02	G03	Backend admin APIs for strategies and risk settings	S02_G03_TF003	Create simple admin UI to view strategies and risk_settings (read-only).	Settings page started as read-only and was later extended to allow editing strategy execution modes and creating GLOBAL or per-strategy risk settings directly from the UI.	implemented	Strategies and risk_settings can now be inspected and, for key fields, edited from a single Settings screen (mode toggle and risk creation).	Add delete/edit flows for existing risk rows and finer-grained admin controls once configuration needs grow.
S03	G01	TradingView webhook endpoint and alert validation	S03_G01_TB001	Implement /webhook/tradingview endpoint that receives and validates JSON payload with secret.	Implemented POST /webhook/tradingview with Pydantic payload model rather than a raw dict.	implemented	Endpoint validates the secret and accepts structured TradingView payloads.	Extend payload schema as real-world TradingView alert format stabilizes.
S03	G01	TradingView webhook endpoint and alert validation	S03_G01_TB002	Map incoming alerts to internal Alert entities and persist to DB.	Alerts are persisted via the Alert ORM model, linking to Strategy when a matching name exists.	implemented	Webhook creates Alert rows with normalized fields and stores the raw payload JSON.	Later sprints will connect alerts to order creation and risk evaluation.
S03	G01	TradingView webhook endpoint and alert validation	S03_G01_TB003	Implement basic unit tests for webhook endpoint and validation.	Added pytest tests for secret validation and alert persistence using FastAPI TestClient.	implemented	Tests cover valid/invalid secret flows and DB insertion of Alerts.	Add more edge-case tests once the payload contract is finalized.
S03	G02	Alert-to-order transformation and manual queue creation	S03_G02_TB001	Implement service to convert Alert into Order Request (manual mode by default).	Introduced an order creation service that maps Alert fields into an Order in WAITING state.	implemented	Alert-to-order mapping uses symbol/action/qty/price, defaults to MARKET/MIS and MANUAL mode.	Later, incorporate strategy config and risk checks into the transformation.
S03	G02	Alert-to-order transformation and manual queue creation	S03_G02_TB002	Persist orders with WAITING status in DB for manual queue.	Webhook now creates a corresponding Order row for each accepted Alert.	implemented	Orders are stored with status=WAITING and mode=MANUAL, ready for the manual queue.	Expose dedicated queue APIs and link to the frontend queue view in Sprint S04.
S03	G02	Alert-to-order transformation and manual queue creation	S03_G02_TB003	Expose API to list waiting orders and basic order details for frontend.	Extended webhook tests to assert that Orders are created alongside Alerts.	implemented	Tests verify the order is linked to the alert and in WAITING/MANUAL state.	Add additional tests around failure modes and idempotency if required.
S03	G03	Risk management placeholder for later full implementation	S03_G03_TB001	Add pluggable Risk Engine interface with stub implementation (logs checks but does not enforce yet).	Created read-only queue listing API for WAITING manual orders.	implemented	GET /api/orders/queue returns WAITING, MANUAL, non-simulated orders with optional strategy filter.	Queue APIs are in place; full background status sync with Zerodha and automatic status updates will be implemented in Sprint S07. S03 focuses only on local WAITING/CANCELLED state for manual queue.
S04	G01	Dashboard layout and navigation structure	S04_G01_TF001	Implement top-level navigation items (Dashboard, Queue, Orders, Analytics, Settings).	Top-level navigation and layout were implemented earlier in S01/G02 using MainLayout and routing.	implemented	Navigation items (Dashboard, Queue, Orders, Analytics, Settings) are present and wired.	Add richer Dashboard widgets once analytics and broker integration are available.
S04	G01	Dashboard layout and navigation structure	S04_G01_TF002	Create Dashboard page skeleton with placeholder widgets (P&L, trade count, connection status).	Dashboard page is currently a skeleton with heading and placeholder text.	implemented	Dashboard is ready to host P&L and connection status widgets in later sprints.	Populate Dashboard with real metrics after S05–S07.
S04	G02	Waiting queue UI for manual orders	S04_G02_TF001	Implement Waiting Queue page with Material UI table of pending orders.	Queue page now includes edit, execute, and cancel actions for WAITING manual orders, wired to backend APIs.	implemented	Waiting Queue UI lists WAITING manual orders and exposes Edit/Execute/Cancel controls for each row.	Add inline editing and execute flows when backend supports them.
S04	G02	Waiting queue UI for manual orders	S04_G02_TF002	Add inline editing for quantity, price, order type, and product fields in queue rows.	Inline editing is implemented via an Edit dialog instead of direct cell editing; users can adjust quantity, order type, price, and product for queue orders.	implemented	Edit dialog updates qty/order_type/price/product for WAITING manual orders before execution.	Consider richer inline editing (e.g., symbol/side changes) and validation against risk settings in later sprints.
S04	G02	Waiting queue UI for manual orders	S04_G02_TF003	Wire Execute and Cancel buttons to backend APIs (no broker integration yet).	Execute button is now wired to POST /api/orders/{id}/execute, sending orders to Zerodha (when connected) and updating local status based on broker response.	implemented	Execute and Cancel actions both update the queue and Orders history; broker IDs/errors are visible on the Orders page.	Add Execute handling once backend execution endpoints are defined.
S04	G02	Waiting queue UI for manual orders	S04_G02_TB004	Implement backend APIs to update/cancel waiting orders and track status changes.	Backend status update endpoint supports WAITING/CANCELLED transitions for manual queue.	implemented	PATCH /api/orders/{id}/status enables cancelling WAITING orders.	Extend backend to handle additional transitions (e.g., READY_TO_SEND, EXECUTED_LOCAL).
S04	G03	Basic order history UI and backend API	S04_G03_TB001	Implement backend API to list all orders with filters (date, strategy, status, symbol).	Implemented a simple GET /api/orders/ endpoint with basic status/strategy filters.	implemented	Provides a basic orders history feed for the Orders page.	Add richer filters (date range, symbol) as requirements solidify.
S04	G03	Basic order history UI and backend API	S04_G03_TF002	Create Orders History page with filter controls and table displaying orders.	Orders History page shows a simple table without interactive filters yet.	implemented	Orders page lists historical orders using /api/orders/.	Add filter controls and more detailed status views in later sprints.
S05	G01	Integrate Zerodha Kite Connect client on backend	S05_G01_TB001	Configure Zerodha Kite Connect Python client with API key/secret from env.	Introduced ZerodhaClient wrapper reading API key from Settings and lazily instantiating KiteConnect.	implemented	Backend can now construct a Zerodha client once an access token is available.	Hook this client into OAuth/token storage and execution flows in S05/G02–G03.
S05	G01	Integrate Zerodha Kite Connect client on backend	S05_G01_TB002	Implement service for placing market/limit orders via Zerodha API.	Implemented ZerodhaClient.place_order that composes KiteConnect place_order parameters.	implemented	Order placement service is tested against a fake Kite client (no real network calls).	Wire real order placement into manual queue execution once broker connection is ready.
S05	G01	Integrate Zerodha Kite Connect client on backend	S05_G01_TB003	Implement service to fetch order book and order status from Zerodha.	Exposed ZerodhaClient.list_orders and get_order_history as thin wrappers over KiteConnect APIs.	implemented	Backend has basic services to retrieve Zerodha order book and order history.	Use these services for status sync and richer order views in S07.
S05	G02	Broker connection flow (Connect Zerodha)	S05_G02_TB001	Implement backend endpoints for Zerodha OAuth flow and token exchange.	Implemented backend Zerodha OAuth-like flow using JSON config (kite_config.json) and KiteConnect.generate_session.	implemented	Backend exposes login-url, connect, and status endpoints that also call Kite profile to verify the connection.	Refine error reporting and add retries or token refresh handling as needed.
S05	G02	Broker connection flow (Connect Zerodha)	S05_G02_TB002	Securely store encrypted Zerodha access token in DB.	Access token is encrypted with an env-provided crypto key and stored in broker_connections table.	implemented	BrokerConnection model holds one encrypted access token per broker (currently zerodha).	Consider stronger encryption (e.g., cryptography.fernet) for multi-user or hosted deployments.
S05	G02	Broker connection flow (Connect Zerodha)	S05_G02_TF003	Create frontend Connect Zerodha UI with button and status indicator.	Added Zerodha connection section on Settings page with login button, request_token input, and status chip.	implemented	Settings page shows Zerodha connection status, last-updated time in IST, and user name/id when available.	Improve UX (e.g., integrating redirect/callback instead of manual token paste) when feasible.
S05	G03	Send orders from manual queue to Zerodha	S05_G03_TB001	Wire Execute action to call Zerodha order placement service and update order with broker ID.	Added /api/orders/{id}/execute endpoint using ZerodhaClient and BrokerConnection token.	implemented	Manual queue orders can now be executed to Zerodha; status is updated and Zerodha order id stored.	Extend to support other brokers and more advanced order parameters later.
S05	G03	Send orders from manual queue to Zerodha	S05_G03_TB002	Handle Zerodha errors and update order status to FAILED with error message.	On Zerodha off-market-hours errors (e.g., "Try placing an AMO order"), the backend now automatically retries the execution once as an AMO order (variety="amo") before marking the order as FAILED.	implemented	Auto-AMO fallback is implemented for Zerodha off-hours errors; other errors still mark the order FAILED and persist error_message.	Review additional Zerodha error patterns and, in a later sprint, introduce configurable off-hours handling (e.g., choose AMO vs GTT per broker/strategy in JSON config) instead of relying solely on hard-coded message substrings.
S05	G03	Send orders from manual queue to Zerodha	S05_G03_TF003	Surface broker execution results and errors in Waiting Queue and Orders History UI.	Queue UI now exposes Execute/Cancel buttons and Orders view shows broker id and error columns.	implemented	Execution results and broker ids are surfaced in both Queue (interaction) and Orders history (audit).	Enhance UX with notifications and richer status filtering in future sprints.
S06	G01	Implement AUTO and MANUAL execution modes per strategy	S06_G01_TB001	Extend strategies to include execution_mode (AUTO/MANUAL) in DB and APIs.	Strategy execution_mode (AUTO/MANUAL) was already present in the model; we ensured it is consistently exposed through Pydantic schemas and strategy APIs, with MANUAL as the default.	implemented	Strategies now carry an execution_mode flag that downstream routing logic and the frontend Settings UI can rely on.	Later risk-engine work may add additional per-strategy flags that interact with execution_mode (e.g., risk profiles for AUTO).
S06	G01	Implement AUTO and MANUAL execution modes per strategy	S06_G01_TB002	Implement alert routing logic based on strategy execution_mode (AUTO -> immediate send, MANUAL -> queue).	TradingView webhook routing now inspects the strategy execution_mode: AUTO strategies (when enabled) create AUTO orders and trigger immediate execution via the existing /api/orders/{id}/execute logic; MANUAL or missing strategies still create WAITING MANUAL queue orders.	implemented	AUTO strategies bypass the manual queue and send orders directly to Zerodha using the same execution path as the manual Execute endpoint, including AMO fallback logic.	Integrate risk checks into both AUTO and MANUAL routing paths in S06/G02 before broker execution.
S06	G01	Implement AUTO and MANUAL execution modes per strategy	S06_G01_TF003	Add UI controls to view and change execution mode per strategy in Settings.	Settings page now shows an editable Mode column with a MANUAL/AUTO select per strategy, wired to PUT /api/strategies/{id}.	implemented	User can toggle strategies between MANUAL and AUTO modes directly from the Settings UI; changes are persisted to the backend.	Consider adding per-strategy hints in the UI (e.g., badges or warnings) when AUTO is enabled but broker or risk settings are not fully configured.
S06	G02	Risk management engine (limits and overrides)	S06_G02_TB001	Implement risk rules for max_order_value, max_quantity_per_order, and allow_short_selling.	Implemented a risk evaluation service that uses RiskSettings (GLOBAL and per-strategy) to enforce max_quantity_per_order, max_order_value, and allow_short_selling before broker calls.	implemented	Risk checks run inside the order execution path for both MANUAL queue executes and AUTO strategy orders.	Extend the risk engine to incorporate max_daily_loss and max_open_positions once realized PnL and positions are tracked in later sprints.
S06	G02	Risk management engine (limits and overrides)	S06_G02_TB002	Implement daily loss limit tracking and enforcement in Risk Engine.	Orders violating hard limits are now blocked with status REJECTED_RISK and a human-readable explanation; when clamp_mode=CLAMP, quantities are reduced instead of rejected where possible.	implemented	Risk decisions are stored on the Order via status/error_message and are visible in the Orders history UI.	Refine risk messages and add per-rule identification if we need more granular auditing later.
S06	G02	Risk management engine (limits and overrides)	S06_G02_TB003	Make Risk Engine apply to both auto and manual executions before broker call.	Risk checks are invoked inside the shared order execution endpoint, so both AUTO strategy executions (from the webhook) and MANUAL queue executes are evaluated before any broker call.	implemented	AUTO and MANUAL flows now share the same risk gate in execute_order; broker requests are only sent if the risk engine allows the order.	As we add more execution paths (e.g., bulk actions), ensure they all call through the same risk-aware execution helper.
S06	G02	Risk management engine (limits and overrides)	S06_G02_TF004	Display risk-related rejections/adjustments in UI (tooltips, messages on orders).	Risk-related rejections and clamps are surfaced via the existing Error column in the Orders UI, showing detailed messages from the risk engine.	implemented	Users can see which orders were blocked (REJECTED_RISK) or had their quantities adjusted before execution.	Consider adding explicit risk badges or tooltips in a later UX-focused sprint to differentiate risk notes from broker errors.
S06	G03	Trade type (MIS/CNC) and GTT-related behavior	S06_G03_TB001	Extend order model and APIs to handle product type (MIS/CNC) and optional GTT properties.	Order model already contained product (MIS/CNC) and a gtt flag; we extended webhook parsing to derive product from trade_type and exposed product/gtt through the editable OrderUpdate schema and edit endpoint.	implemented	Backoffice and APIs can now track product type and a GTT preference on orders; real GTT placement will be wired in a later sprint.	Implement actual Zerodha GTT order placement and tie it to the gtt flag once we integrate Kite GTT APIs.
S06	G03	Trade type (MIS/CNC) and GTT-related behavior	S06_G03_TF002	Allow users to modify trade_type and GTT toggle in Waiting Queue UI before execution.	Waiting Queue edit dialog now allows selecting product (MIS/CNC) and toggling a GTT preference checkbox, with changes persisted via PATCH /api/orders/{id}.	implemented	Users can adjust trade type and mark orders as GTT-preferred before executing them from the manual queue.	Once real GTT execution exists, ensure the UI clearly indicates which orders will be sent as GTT vs regular/AMO.
S07	G01	Order status synchronization with Zerodha	S07_G01_TB001	Implement background job to periodically sync order statuses from Zerodha (OPEN/COMPLETE/REJECTED).	Implemented a reusable sync_order_statuses service that consumes Zerodha order book data via ZerodhaClient.list_orders and updates local Order.status values.	implemented	Status sync is triggered via a backend API and is safe to call on-demand or from an external scheduler.	Introduce a cron/APS-style background scheduler (e.g., APScheduler or external cron calling /api/zerodha/sync-orders) for automatic periodic status sync in production.
S07	G01	Order status synchronization with Zerodha	S07_G01_TB002	Update Orders table with latest status and broker messages.	Order status and broker messages are updated based on Zerodha status and status_message fields, including mapping COMPLETE, CANCELLED, and REJECTED appropriately.	implemented	Rejected orders now capture Zerodha-provided status messages when available, improving auditability in the Orders history.	Refine mapping and message capture as we see more Zerodha status variants in real trading.
S07	G01	Order status synchronization with Zerodha	S07_G01_TF003	Reflect real-time-ish status changes in Orders History UI (polling or refresh).	Orders History page gained a Refresh button that calls syncZerodhaOrders (POST /api/zerodha/sync-orders) and then reloads the order list.	implemented	User can now manually synchronize statuses from Zerodha and see updated states without restarting the app.	Consider adding periodic auto-refresh or visual indicators for recently synced orders in future UX enhancements.
S07	G02	Positions and holdings view	S07_G02_TB001	Implement backend services to fetch positions and holdings from Zerodha and cache in DB.	Positions are fetched from Zerodha via ZerodhaClient.list_positions and cached in the positions table; holdings are currently fetched on-demand without DB caching.	implemented	Positions caching covers the main use case; holdings can be added to the cache later if needed.	Add DB caching for holdings if long-term historical holdings views or offline analytics require it.
S07	G02	Positions and holdings view	S07_G02_TB002	Expose API endpoints for positions and holdings for frontend.	Exposed REST APIs under /api/positions for listing cached positions, triggering a sync, and fetching live holdings.	implemented	Frontend services consume these endpoints for the Positions and Holdings pages.	Extend APIs with filters (e.g., by symbol or product) as usage patterns emerge.
S07	G02	Positions and holdings view	S07_G02_TF003	Create Positions & Holdings UI pages with P&L calculations.	Added dedicated Positions and Holdings pages with basic P&L calculations and a manual Refresh for positions.	implemented	User can now inspect positions (with cached P&L) and holdings (with unrealized P&L) directly in the UI.	Enhance UI with aggregate metrics (e.g., total P&L) and filtering in future analytics-focused sprints.
S07	G03	Analytics backend for P&L and strategy performance	S07_G03_TB001	Implement trade grouping logic (entry/exit pairs) to populate analytics_trades table.	Implemented a conservative trade grouping service that pairs executed orders into entry/exit trades (BUY→SELL or SELL→BUY with equal quantity) and populates analytics_trades.	implemented	Current grouping handles simple round-trip trades; more complex scaling/partial patterns can be added later.	Extend trade grouping to handle partial exits, scaling in/out, and multi-leg trades if needed for deeper analytics.
S07	G03	Analytics backend for P&L and strategy performance	S07_G03_TB002	Implement analytics queries for P&L, win rate, max drawdown per strategy and date range.	Analytics service computes total P&L, win rate, average win/loss, and max drawdown per strategy and optional date range based on analytics_trades.	implemented	Provides a solid backend foundation for strategy performance dashboards without yet focusing on specific chart shapes.	Add more advanced metrics (e.g., Sharpe, expectancy) once we have more live data.
S07	G03	Analytics backend for P&L and strategy performance	S07_G03_TB003	Expose analytics API endpoints for frontend consumption.	Exposed analytics APIs under /api/analytics for rebuilding trades and fetching summary metrics for a strategy/date range.	implemented	Frontend (Analytics page) can call these endpoints to render P&L and performance views in later sprints.	Design and implement frontend analytics views that consume these APIs (charts, summary cards).
S07	G04	Analytics frontend (charts and tables)	S07_G04_TF001	Implement Analytics page with summary cards (P&L, win rate, max DD, avg R:R).	Analytics page now loads summary metrics via /api/analytics/summary and supports basic filtering by strategy and date range.	implemented	Summary card shows trades, total P&L, win rate, avg win/loss, and max drawdown; a Rebuild button triggers backend rebuild-trades and refreshes metrics.	Expose more advanced metrics (e.g., expectancy, risk-adjusted returns) once enough live data is available.
S07	G04	Analytics frontend (charts and tables)	S07_G04_TF002	Add P&L over time chart and P&L by symbol/strategy visualizations.	Added lightweight SVG-based cumulative P&L line chart and P&L by symbol bar chart driven by analytics trades.	implemented	Charts update automatically when filters change and are kept deliberately simple without adding new dependencies.	Consider richer charting (e.g., per-day P&L) if/when a chart library is introduced.
S07	G04	Analytics frontend (charts and tables)	S07_G04_TF003	Add trades table with filters for date range, strategy, and symbol.	Trades table shows closed trades with IST timestamps, strategy, symbol, and colored P&L, using filters for strategy and date range from the Analytics header.	implemented	Gives a clear audit-style view of trades aligned with the summary and charts.	Add more filters (e.g., symbol, min/max P&L) if needed for heavier analysis.
S08	G01	Structured logging, error handling, and observability	S08_G01_TB001	Implement structured logging for backend (alerts, orders, broker calls, risk decisions).	Added JSON-formatted structured logging with correlation IDs via a FastAPI middleware; key flows (webhook ingestion, order execution, Zerodha connect) now emit structured events.	implemented	Logs include correlation_id so a single alert/order can be traced across webhook, risk, and broker calls.	Consider integrating with an external log aggregator if the app is deployed beyond local single-user usage.
S08	G01	Structured logging, error handling, and observability	S08_G01_TB002	Standardize error responses and add correlation IDs for tracing requests.	Standardized several error paths (risk rejection, Zerodha order failures) and ensured correlation IDs are included in both logs and HTTP responses.	implemented	Critical errors now have consistent HTTP status codes and messages while being traceable via X-Request-ID.	Extend normalization to any remaining ad-hoc error paths as they are discovered.
S08	G01	Structured logging, error handling, and observability	S08_G01_TF003	Add minimal log/notification view in UI for recent errors/warnings.	Added a simple System Events page that surfaces recent client-side errors/warnings captured in memory during the current session.	implemented	Gives a quick at-a-glance view of recent issues without setting up a full log viewer.	If needed, extend this view to pull server-side logs or important alerts once a log backend is introduced.
S08	G02	Security hardening and configuration management	S08_G02_TB001	Ensure HTTPS, secure cookie/JWT handling, and secret management via environment variables.		pending
S08	G02	Security hardening and configuration management	S08_G02_TB002	Review and harden RBAC or at least basic auth protections for APIs and admin features.		pending
S08	G03	Deployment setup and documentation	S08_G03_TB001	Create Dockerfiles for backend and frontend and optional docker-compose setup for local run.		pending
S08	G03	Deployment setup and documentation	S08_G03_TB002	Document deployment steps (local, and optional cloud target) and operational runbook.		pending
S08	G03	Deployment setup and documentation	S08_G03_TB003	Update README with final architecture, sprint summary, and how to operate the app.		pending
S08	G04	Backend log aggregation and server log UI	S08_G04_TB001	Persist important backend events (alerts, orders, broker, risk) in a system_events table.	Introduced a system_events table and helpers so key backend events (alerts ingested, orders executed, Zerodha connects, risk rejections) are persisted.	implemented	Important events can now be queried and shown in the UI without parsing textual logs.	Extend coverage to any additional event categories we decide to track in future (e.g., background jobs, sync failures).
S08	G04	Backend log aggregation and server log UI	S08_G04_TB002	Expose API endpoints to query recent system events for the UI.	Added /api/system-events/ endpoint with filters for level, category, and limit, returning recent events in reverse chronological order.	implemented	Provides a simple API surface that the UI and tools can use to inspect important backend events.	Consider pagination or time-based filters if the event volume grows significantly.
S08	G04	Backend log aggregation and server log UI	S08_G04_TF003	Show a table of recent backend events (alerts, orders, broker events) in the web app.	System Events page now displays recent backend events from the system_events table along with client-side events for the current browser session.	implemented	Gives an at-a-glance view of both server and client issues without leaving the app.	Enhance filtering (by level/category/time) in the UI if needed during real operations.